## Main Register
Register of activity which has potential to impact on the Freight and Heavy Haulage Industry (in planning, design, soon to start, construction phase or complete) |  |  | This register holds basic details of activity resulting in State Highway Closures, Detours, Weight or Dimensional restrictions only
KEY
NEW / AMENDED | Last Updated 18/04/2024 |  | For details of the many Speed and infrastructure projects across the country, click here
REMOVED
REGION (add extra rows when needed) | PROJECT / EVENT NAME | SH | Vehicle Type affected (Over Dimension, HPMV, 50Max, all frieght) | Impact Rating | RESTRICTION DESCRIPTION | DETOUR DESCRIPTION (if needed) | RESTRICTION START (date) planned or past | PLANNED REMOVAL OF RESTRICTION (date) | Confidence in start date | CONTACT FOR ACTIVITY | CONTACT DETAILS | PROJECT LINK / WEBSITE | Time Day | Complete Y/N | Modified This Week
Wellington Transport Alliance (WTA) | Wings Over Wairarapa - Masterton Airfield 2025 | 2 | all | 4 | Delays | n/a | 2025-11-24 | 2025-11-26 | +/- 6 months | - | Kerry Smith | kerry@mdc.govt.nz | Day | N | Yes
Marlborough Roads | SH1 Blenheim Main Street Level Crossing - Full Closure | 1S | All Freight | 4 | Detour via Lewis Pass possible | - | 2025-05-01 | 2025-05-03 | +/- 3 months | - | - | - | All | N | No
Wellington Transport Alliance (WTA) | Proposed SH58 Safety Improvements SUPERWEEKEND - full closure of SH58 TG interchange to Flightys Rd, Friday 7pm to Monday 5am | 58 | All | 4 | Full closure/detour | - | 2025-04-01 | 2025-04-30 | +/- month | y | 713257 | - | All | N | No
Wellington Transport Alliance (WTA) | CubaDupa 2025 - Lane closure on Vivian Street | LR | All | 3 | Delays | N/A | 2025-03-22 | 2025-03-25 | +/- a week | denise Beazley | denise.beazley@wcc.govt.nz | - | All | N | No
Wellington Transport Alliance (WTA) | WTA SH2 Remutaka Hill 5 Night Closure - March 1 of 2 (TBC) - Sun-Thur nights | 2 | all | 4 | Closure with long detour | Long Detour (aprox 2hrs) via Pahiatua | 2025-03-10 | 2025-03-15 | +/- a week | Felicity Glynn | Lisa Henderson | asheesh.chand@wta.nzta.govt.nz | Night | N | Yes
Wellington Transport Alliance (WTA) | Martinborough Fair 2025 (2 of 2) - first Saturday of February and March annually | 53 | All | 3 | Delays | N/A | 2025-03-01 | 2025-03-01 | sure | - | tim Langley | tim.langley@swdc.govt.nz | Day | N | Yes
Wellington Transport Alliance (WTA) | Toast Martinborough 2025 - no 2024 festival | 53 | All | 3 | Delays | N/A | 2025-02-19 | 2025-02-19 | +/- month | tim.langley@swdc.govt.nz | https://www.martinborough-village.co.nz/page/Toast_Martinborough/ | - | All | N | Yes
Wellington Transport Alliance (WTA) | Wellington Round the Bays Fun Run 2025 (6:30am to 1pm) | 1N | all | 3 | Delays | Local Roads | 2025-02-18 | 2025-02-18 | +/- a week | - | - | - | Day | N | No
Wellington Transport Alliance (WTA) | Martinborough Fair 2025 (1 of 2) - first Saturday of February and March annually | 53 | All | 3 | Delays | N/A | 2025-02-01 | 2025-02-01 | sure | - | tim Langley | tim.langley@swdc.govt.nz | Day | N | Yes
Gisborne TREC | Gisborne Anniversary Weekend 2025 | All | All | 4 | delays | - | 2025-01-24 | 2025-01-28 | sure | - | - | - | All | N | No
Wellington Transport Alliance (WTA) | WTA SH2 Remutaka Hill 1 Night Closure - January (TBC) | 2 | all | 4 | Closure with long detour | Long Detour (aprox 2hrs) via Pahiatua | 2025-01-14 | 2025-01-15 | +/- a week | Felicity Glynn | Lisa Henderson | asheesh.chand@wta.nzta.govt.nz | Night | N | No
Wellington Transport Alliance (WTA) | O2NL Otaki to North of Levin - Manawatu Section - NZ Upgrade Programme | 1N | All | 4 | Potential delays | N/A | 2025-01-01 | 2030-01-01 | +/- 12 months | - | Raewyn Pudsey | raewyn.pudsey@nzta.govt.nz | All | N | No
Gisborne TREC | SH35 Makorori Active Slip Site (likely future construction) | 35 | All | 3 | Delays due to stop go operation | - | 2025-01-01 | 2026-01-01 | +/- 12 months | - | - | - | All | N | No
Nelson Tasman | Tahunanui Nelson Future Access Project | 6 | - | 3 | - | - | 2025-01-01 | 2026-01-01 | +/- a week | Leanne Scott | Anna Sanson | Anna.Sanson@nzta.govt.nz | All | N | No
Gisborne TREC | Fire in the Sky - Fireworks NYE 2024_25 | 35 | All | 3 | delays | N/A | 2024-12-31 | 2025-01-01 | sure | - | - | - | All | N | No
Gisborne TREC | Rythm and Vines Festival - Waiohika Estate 2024 | 2 | All | 3 | delays | n/A | 2024-12-29 | 2024-12-31 | sure | - | - | - | all | N | No
Gisborne TREC | Gisborne A&P Show - Animal Transport Days - Avoid Long TTM DELAYS during the day | All | Daytime | 3 | More Animal Transporters | - | 2024-12-16 | 2024-12-20 | sure | - | - | - | Day | N | No
Gisborne TREC | Gisborne A&P Show - Public Days | All | Daytime | 3 | Some delays around A&P Grounds | - | 2024-12-16 | 2024-12-20 | sure | - | - | - | Day | N | No
Wellington Transport Alliance (WTA) | Arras Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night DEC 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-12-11 | 2024-12-12 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | Mt Victoria Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night DEC 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-12-10 | 2024-12-11 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | Terrace Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night DEC 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-12-09 | 2024-12-10 | sure | - | - | - | Night | N | Yes
South Canterbury | SH1 ChipSealing Program Rakaia - Timaru | 1S | All | 4 | Stop/Go potentially day and night TBC | - | 2024-11-19 | 2024-12-22 | +/- a week | - | - | - | Day | N | No
Wellington Transport Alliance (WTA) | Mt Victoria Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night NOV 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-11-12 | 2024-11-13 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | Terrace Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night NOV 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-11-11 | 2024-11-12 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | WTA SH2 Remutaka Hill 5 Night Closure - November (TBC) - Sun-Thur nights | 2 | all | 4 | Closure with long detour | Long Detour (aprox 2hrs) via Pahiatua | 2024-11-03 | 2024-11-08 | sure | Felicity Glynn | Lisa Henderson | asheesh.chand@wta.nzta.govt.nz | Night | N | Yes
Wellington Transport Alliance (WTA) | Pāuatahanui Lamb and Calf Day 2024 | 58 | All | 3 | Delays | N/A | 2024-11-02 | 2024-11-02 | sure | N/A | N/A | - | Day | N | Yes
Wellington Transport Alliance (WTA) | Proposed SH58 Safety Improvements SUPERWEEKEND - full closure of SH58 TG interchange to Flightys Rd, Friday 7pm to Monday 5am | 58 | All | 4 | Full closure/detour | - | 2024-11-01 | 2024-11-30 | +/- month | y | 713257 | - | All | N | Yes
Wellington Transport Alliance (WTA) | WTA SH2 Remutaka Hill 1 Night Closure - October (TBC) | 2 | all | 4 | Closure with long detour | Long Detour (aprox 2hrs) via Pahiatua | 2024-10-13 | 2024-10-13 | sure | Felicity Glynn | Lisa Henderson | asheesh.chand@wta.nzta.govt.nz | Night | N | Yes
Wellington Transport Alliance (WTA) | Arras Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night OCT 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-10-09 | 2024-10-10 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | Mt Victoria Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night OCT 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-10-08 | 2024-10-09 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | Terrace Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night OCT 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-10-07 | 2024-10-08 | sure | - | - | - | Night | N | Yes
South Canterbury | SH1 Timaru Newmans - Structural AC | 1S | All | 3 | Stop/Go | - | 2024-10-02 | 2024-12-12 | +/- Month | TBC | - | - | Night | N | No
Hawkes Bay TREC | SH2 TBC Recovery Project | 2 | All | 3 | Delays | n/a | 2024-10-01 | 2026-01-01 | +/- 12 months | - | - | - | All | N | No
Wellington Transport Alliance (WTA) | Carterton Daffodil Festival 2024 - Likely Full Closure with Local Road Detour | 2 | n/a | 3 | Detour | n/a | 2024-09-15 | 2024-09-15 | sure | - | - | - | Day | N | Yes
Wellington Transport Alliance (WTA) | Mt Victoria Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night SEP 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-09-10 | 2024-09-11 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | Terrace Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night SEP 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-09-09 | 2024-09-10 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | WTA SH2 Remutaka Hill 5 Night Closure - September (tentative second week) - Sun-Thur nights | 2 | all | 4 | Closure with long detour | Long Detour (aprox 2hrs) via Pahiatua | 2024-09-08 | 2024-09-13 | sure | Felicity Glynn | Lisa Henderson | asheesh.chand@wta.nzta.govt.nz | Night | N | Yes
Wellington Transport Alliance (WTA) | WTA SH2 Remutaka Hill 5 Night Closure - September (TBC) - Sun-Thur nights | 2 | all | 4 | Closure with long detour | Long Detour (aprox 2hrs) via Pahiatua | 2024-09-01 | 2024-09-06 | sure | Felicity Glynn | Lisa Henderson | asheesh.chand@wta.nzta.govt.nz | Night | N | Yes
Gisborne TREC | Labour Day 2024 | All | All | 4 | delays | N/A | 2024-08-30 | 2024-08-02 | sure | - | - | - | Day | N | No
Wellington Transport Alliance (WTA) | Arras Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night AUG 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-08-14 | 2024-08-15 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | Mt Victoria Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night AUG 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-08-13 | 2024-08-14 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | Terrace Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night AUG 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-08-12 | 2024-08-13 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | WTA SH2 Remutaka Hill 1 Night Closure - August (TBC) | 2 | all | 4 | Closure with long detour | Long Detour (aprox 2hrs) via Pahiatua | 2024-08-11 | 2024-08-12 | sure | Felicity Glynn | Lisa Henderson | asheesh.chand@wta.nzta.govt.nz | Night | N | -
West Waikato | SH1 C2P Gorton Road section - turnaround and WRB | 1N | All Freight | 4 | Southbound detour - via Taotaoroa Road | Karapiro Road, Taotaoroa Road, SH29 | 2024-08-01 | 2024-12-01 | sure | Tracee Parr | Glenys Farries | west.waikato@fultonhogan.com | All | N | No
South Canterbury | SH1 Showgrounds Culvert Replacement | 1S | All Freight | 4 | Delays | - | 2024-07-30 | 2024-07-30 | sure | - | - | - | Day | N | No
East Waikato | SH29 Kaimai Range FULL NIGHTIME CLOSURES July | 29 | All Freight | 4 | Road closed between 8.00pm and 3.30am for 4 nights. Alternative route required | - | 2024-07-14 | 2024-07-17 | +/- a week | - | Ali Ayoubi | ewnoc@higgins.co.nz | Night | N | No
Wellington Transport Alliance (WTA) | Mt Victoria Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night JUL 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-07-09 | 2024-07-10 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | Terrace Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night JUL 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-07-08 | 2024-07-09 | sure | - | - | - | Night | N | Yes
Gisborne TREC | SH35 Large Scour Site (likely future construction) | All | All Freight | 3 | Delays due to stop go operation | - | 2024-07-01 | 2025-07-01 | +/- 12 months | - | - | - | All | N | No
Gisborne TREC | SH35 Big Underslip (likely future construction) | 35 | All Freight | 3 | Delays due to stop go operation | - | 2024-07-01 | 2025-01-01 | +/- 3 months | - | - | - | All | N | No
Gisborne TREC | SH35 Washout Site (likely future construction) | 35 | All Freight | 3 | Delays due to stop go operation | - | 2024-07-01 | 2025-01-01 | +/- 3 months | - | - | - | All | N | No
Wellington Transport Alliance (WTA) | SH2 Hebden Crescent - permanent closure of southern access road to SH2 to/from Hebden Cresent | 2 | All Freight | 4 | Closure of access in and out of Hebden Cres, requiring safer detour | Detour via Manor Park Interchange with SH58 | 2024-07-01 | 2024-07-15 | +/- a week | David Cross | David Cross | sh2huttvalley@nzta.govt.nz | All | N | No
West Waikato | SH1 Cambridge Expressway - Asphalt resurfacing site | 1N | All Freight | 3 | Southbound lanes closed with contraflow in place on northbound lanes under stop/go Southbound on-ramp at Lockley Road closed | No detour | 2024-07-01 | 2024-07-03 | +/- Month | Glenys Farries | west.waikato@fultonhogan.com | - | All | N | -
Hawkes Bay TREC | Full road closure of SH2 between Watchman Road and Prebensen Drive, Closure is between 8pm to 5am (Night time only). | 2 | All Freight | 3 | Minor delays are expected along this route. | Local detours will be in place for traffic, via Meeanee Quay, Pandora Road, Hyderabad Road and Prebensen Drive. This route is suitable for all vehicles. | 2024-06-30 | 2024-06-30 | sure | - | martin.colditz@trec.nz | - | Night | N | No
Gisborne TREC | Matariki 2024 | All | All Freight | 4 | delays | N/A | 2024-06-28 | 2024-06-28 | sure | - | - | - | Day | N | No
Wellington Transport Alliance (WTA) | Wellington Marathon 2024 | 1N | all | 3 | Delays and Detour | local Road Detours | 2024-06-23 | 2024-06-23 | sure | - | denise Beazley | denise.beazley@wcc.govt.nz | Day | N | No
Wellington Transport Alliance (WTA) | WTA SH2 Remutaka Hill 5 Night Closure - June - Sun-Thur nights | 2 | all | 4 | Closure with long detour | Long Detour (aprox 2hrs) via Pahiatua | 2024-06-16 | 2024-06-21 | sure | Felicity Glynn | Lisa Henderson | asheesh.chand@wta.nzta.govt.nz | Night | N | Yes
Hawkes Bay TREC | Full road closure of SH2 between Prebensen Drive and Taradale Road,Closure is between 8pm to 5am (Night time only) | 2 | All Freight | 3 | Minor delays are expected along this route. | Local detours will be in place for traffic, via Ford Road and Austin Street. This route is suitable for all vehicles. | 2024-06-16 | 2024-06-16 | sure | - | martin.colditz@trec.nz | - | Night | N | No
Wellington Transport Alliance (WTA) | Arras Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night JUN 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-06-12 | 2024-06-13 | sure | Felicity Glynn | - | - | Night | N | No
Wellington Transport Alliance (WTA) | Mt Victoria Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night JUN 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-06-11 | 2024-06-12 | sure | Felicity Glynn | - | - | Night | N | No
Wellington Transport Alliance (WTA) | Terrace Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night JUN 2024 | 1N | all | 3 | Delays and Detour | Standard Waterfront Detour | 2024-06-11 | 2024-06-11 | sure | Felicity Glynn | - | - | Night | N | No
South Canterbury | SH1 St Andrews SIP Project - Phase 1 Median Barrier Construction | 1S | all | 3 | Delays | - | 2024-06-10 | 2024-12-10 | +/- 3 months | TBC | - | - | All | N | No
Gisborne TREC | Kings Birthday 2024 | All | All Freight | 4 | delays | N/A | 2024-06-03 | 2024-06-03 | sure | - | - | - | Day | N | No
Hawkes Bay TREC | Full road closure of SH2 between Taradale Road and Meeanee Road,Closure is between 8pm to 5am (Night time only). | 2 | All Freight | 3 | Minor delays are expected along this route | Local detours will be in place for light traffic, via Taradale Road, Kennedy Road, Gloucester Street, Guppy Road and Meeanee Road. HPMV detour, via Taradale Road, Kennedy Road, Gloucester Street, Lee Road, and Meeanee Road | 2024-06-02 | 2024-06-02 | sure | - | martin.colditz@trec.nz | - | Night | N | No
Auckland System Management (ASM) | Old SH1 - Warkworth (Between Hudson Road and Hill Street) | 1N | All Freight | 3 | Urgent culvert replacement (Storm damaged/Emergency works) is being planned. Potential full closure for 36hr within the next 4 weeks. More to follow when known. | - | 2024-06-01 | 2026-01-01 | +/- Month | - | - | - | All | N | No
Wellington Transport Alliance (WTA) | Moonshine Road Roundabout - NZUP | 58 | All | 3 | Delays and potential closures/detours | N/A | 2024-06-01 | 2025-06-01 | +/- 3 months | tBC | Graham Taylor | graham.taylor@nzta.govt.nz | All | N | No
Wellington Transport Alliance (WTA) | SH58 Flighty's Rd Roundabout - NZ UP | 58 | All | 3 | Delays and potential closures/detours | N/A | 2024-06-01 | 2025-06-01 | +/- 3 months | tBC | Graham Taylor | graham.taylor@nzta.govt.nz | All | N | No
North Canterbury | SH1 SIP Templeton to Selwyn River - Implementation (Rolleston to Selywn) | 1S | All Freight | 3 | TBC - Probably lane diversions and TSL during enabling works | - | 2024-06-01 | 2025-06-01 | +/- 12 months | - | - | - | Day | N | No
Wellington Transport Alliance (WTA) | SH58 Safety Improvements Stage 2B - TG End | 58 | All | 4 | Delays | N/A | 2024-06-01 | 2025-01-01 | +/- 6 months | TBC | Graham Taylor | graham.taylor@nzta.govt.nz | Night | N | No
Marlborough Roads | SH6 SIP Roundabout Tancred / Blenheim Airport Roundabout Construction - Stage Two | 6 | All Freight | 4 | One-way closure with local detour | local Road Detours | 2024-06-01 | 2024-12-01 | +/- 3 months | Clare Fraser | Jacob Ireland | Jacob.Ireland@wsp.govt.nz | All | N | No
Wellington Transport Alliance (WTA) | Otaki Bridge Cycle Clip on (Periods of one lane closed) OLD SH1 | 1N | All Freight | 3 | Delays | - | 2024-06-01 | 2024-09-01 | +/- month | - | - | - | all | N | No
West Waikato | SH31 - FULL DAYTIME CLOSURES - Kawhia | 31 | All Freight | 4 | Road closure between 08:00am and 05:00pm with an opening between 12:00pm and 13:00pm (midday) | - | 2024-06-01 | 2024-06-30 | +/- Month | - | Glenys Farries | west.waikato@fultonhogan.com | All | N | No
West Coast | SH73 McGraths Bridge - Structures (1-2 overnight closure) | 73 | All Freight | 4 | Road Closure overnight TBC | Detour via SH7 Lewis Pass | 2024-06-01 | 2024-06-03 | +/- Month | - | - | - | Night | N | No
Gisborne TREC | Asphalting programme - SH35 Customhouse Street, Childers Road - NIGHT CLOSURE, DETOURS IN PLACE 1900hrs - 0500hrs | 35 | All freight | 4 | Closure with detour | Detours are being checked and agreed with the local authority | 2024-05-28 | 2024-06-04 | +/- a week | - | - | - | Night | N | Yes
North Canterbury | SH74 Lyttelton Tunnel - Deluge System Testing | 74 | All Freight | 3 | Full Closures 11pm - 5am with openings every hour to clear traffic | TBC if detour intended. Openings on the hour | 2024-05-28 | 2024-05-30 | +/- month | - | Southernlink Canterbury NOC | Rosemary Annandale 0274312151 Rosemary.Annandale@downer.co.nz | Night | N | Yes
Wellington Transport Alliance (WTA) | Terrace Tunnel Maintenance Closure (9pm to 5:30am) - 5 Nights MAY 2 of 2 - Sun-Thur nights | 1N | all | 3 | Full closure/detour | Standard Waterfront Detour | 2024-05-26 | 2024-05-31 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | WTA SH2 Remutaka Hill 5 Night Closure - May 2 of 2 Sun-Thur nights | 2 | all | 4 | Closure with long detour | Long Detour (aprox 2hrs) via Pahiatua | 2024-05-26 | 2024-05-31 | sure | Felicity Glynn | Lisa Henderson | asheesh.chand@wta.nzta.govt.nz | Night | N | Yes
Wellington Transport Alliance (WTA) | WTA_AWPT_23_06 SH2 Carterton - full directional closures | 2 | All | 4 | Unidirectional closures/detour | N/A | 2024-05-26 | 2024-06-06 | +/- 2 weeks | Lisa Henderson | lisa.henderson@wta.nzta.govt.nz | - | Night | N | -
Gisborne TREC | Asphalting programme - SH35 Kaiti Mall to Mathews Road - NIGHT CLOSURE, DETOURS IN PLACE 1900hrs - 0500hrs | 35 | All freight | 4 | Closure with detour | Detours are being checked and agreed with the local authority | 2024-05-21 | 2024-05-26 | +/- a week | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | Terrace Tunnel Maintenance Closure (9pm to 5:30am) - 5 Nights MAY 1 of 2 - Sun-Thur nights | 1N | all | 3 | Full closure/detour | Standard Waterfront Detour | 2024-05-19 | 2024-05-24 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | WTA SH2 Remutaka Hill 5 Night Closure - May 1 of 2 - Sun-Thur nights | 2 | all | 4 | Closure with long detour | Long Detour (aprox 2hrs) via Pahiatua | 2024-05-19 | 2024-05-24 | sure | Felicity Glynn | Lisa Henderson | asheesh.chand@wta.nzta.govt.nz | Night | N | Yes
Wellington Transport Alliance (WTA) | WTA_HT_23_02 hazardous tree removal SH1 btwn Grenada/Tawa - nighttime SB full closures | 1N | - | 3 | Full closure/detour | - | 2024-05-19 | 2024-05-31 | sure | - | - | - | Night | N | No
Wellington Transport Alliance (WTA) | WTA_TAC_23_02/03 - Chapel St north of Renall St | 2 | All | 4 | Full closure/detour | N/A | 2024-05-19 | 2024-05-23 | sure | lisa.henderson@wta.nzta.govt.nz | - | - | Night | N | No
East Waikato | SH29 Kaimai Range FULL NIGHTIME CLOSURES May | 29 | All Freight | 4 | Road closed between 8.00pm and 3.30am for 4 nights. Alternative route required | - | 2024-05-19 | 2024-05-22 | +/- a week | - | Ali Ayoubi | ewnoc@higgins.co.nz | Night | N | No
Hawkes Bay TREC | Full road closure of State Highway Two (SH2) between Meeanee Road and Links Road, Closure is between 8pm to 5am (Night time only) | 2 | All Freight | 3 | Minor delays are expected along this route.*THERE IS NO SUITABLE ROUTE FOR HPMV’S * | Local detours will be in place for light traffic, via Meeanee Road, Awatoto Road, SH51, Te Ara Kahikatea, and Pakowhai Road This route is suitable for most vehicles. *THERE IS NO SUITABLE ROUTE FOR HPMV’S * | 2024-05-19 | 2024-05-19 | sure | - | Martin Colditz | martin.colditz@trec.nz | Night | N | No
Wellington Transport Alliance (WTA) | WTA - AWPT_22_05 SH2 Masterton High St | 2 | All | 4 | Full closure/detour | N/A | 2024-05-14 | 2024-06-05 | sure | Lisa Henderson | lisa.henderson@wta.nzta.govt.nz | - | Night | N | No
Wellington Transport Alliance (WTA) | Mt Victoria Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night MAY 2024 | 1N | all | 3 | Full closure/detour | Standard Waterfront Detour | 2024-05-14 | 2024-05-15 | sure | Felicity Glynn | - | - | Night | N | No
Gisborne TREC | Asphalting programme - SH35 Crawford Road to Kaiti Mall - NIGHT CLOSURE, DETOURS IN PLACE 1800hrs - 0600hrs | 35 | All freight | 4 | Closure with detour | Detours are being checked and agreed with the local authority | 2024-05-13 | 2024-05-19 | +/- a week | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | Terrace Tunnel Maintenance Closure (9pm to 5:30am) - 1 Night MAY 2024 | 1N | all | 3 | Full closure/detour | Standard Waterfront Detour | 2024-05-13 | 2024-05-14 | sure | Felicity Glynn | - | - | Night | N | No
Wellington Transport Alliance (WTA) | TBC - BACKUP DATES SH1 Whakahoro southern end of bridge 24/7 stop/go Sun 8pm-Thurs | 1N | All | 3 | Delays | - | 2024-05-12 | 2024-05-16 | sure | - | - | - | All | N | Yes
North Canterbury | SH1 Selwyn River Bridge - Beam and Joint repairs | 1S | All Freight | 4 | Single-lane and 20 minute closures between 10pm and 5am Sunday - Friday nights. Overdimension loads must coordinate with the project team in advance | No detours planned | 2024-05-07 | 2024-07-30 | +/- 2 weeks | - | Smith C&C | Javier Lascar 0274334108 Daniel Gardiner 0272805341 | Night | N | Yes
Coastal Otago | SH1 Ramrock Road in Waikouaiti | 01S | All Freight | 3 | Single lane closure with MTC, 30TSL and side Road closure. Day shift 6am to 6pm. | N/A | 2024-05-06 | 2024-05-17 | +/- a week | - | - | dcc@dcc.govt.nz | Day | N | Yes
Coastal Otago | SH1 Braeside Culvert Replacement - Single Lane with Northbound Detour | 1S | All Freight | 3 | single lane closures 24/7 with detour | North bound traffic detoured via Riccarton Road, Gladstone Road, Quarry Road and back onto SH1 | 2024-05-06 | 2024-05-10 | +/- a week | - | 21482535 | john.oneill@nzta.govt.nz | - | N | Yes
Wellington Transport Alliance (WTA) | SH1 Whakahoro southern end of bridge 24/7 stop/go Sun 8pm-Thurs | 1N | All | 3 | Delays | - | 2024-05-05 | 2024-05-09 | sure | - | - | - | All | N | Yes
Bay of Plenty West | SH2 - Balance Rework (Marina intersection to Totara intersection) | 2 | All Freight | 3 | From 08:30pm to 05:30am roads will be closed with contraflow. Closure dates: 05/05/24-09/05/24; 12/05/24-16/05/24; 19/05/24-21/05/24 | Follow signposted detours | 2024-05-05 | 2024-05-21 | +/- month | Downer | Downer | Wade.Thomas@downer.co.nz | Night | N | No
Bay of Plenty West | SH2 - Baylink Project - Gantry Works | 2 | All Freight | 3 | From 07:00pm to 05:00am - Southbound road closure of Maunganui Road at Concord Avenue | Travelling from Maunganui Rd southbound, detour via Concord Ave, Ocean Beach Rd, Girven Rd | 2024-05-05 | 2024-05-09 | Sure | - | Paul Willey | baylink@nzta.govt.nz | Night | N | No
Bay of Plenty West | SH2 - Baylink Project - Gantry Works | 2 | All Freight | 3 | From 10:00pm to 05:00am - Road closure of Maunganui Rd southbound at Concord Ave | Travelling from Maunganui Rd southbound, detour via Concord Ave, Ocean Beach Rd, Girven Rd | 2024-05-05 | 2024-05-09 | Sure | - | Paul Willey | baylink@nzta.govt.nz | Night | N | No
Bay of Plenty West | SH29A - Baylink Project - Gantry Works | 29A | All Freight | 3 | From 07:00pm to 05:00am - Road closure SH29A westbound at SH29A RAB/Truman Lane/Te Maunga interchange | Travelling from Truman Ln westbound, detour via SH29A roundabout, Te Maunga interchange, Maunganui Rd NB, Hewletts Rd, Takitimu Dr/SH2, Elizabeth St, Cameron Rd, Fifteenth Ave, Turret Rd, Welcome Bay Link Rd | 2024-05-05 | 2024-05-09 | sure | - | Paul Willey | baylink@nzta.govt.nz | Night | N | No
Wellington Transport Alliance (WTA) | WTA_ITS_23_65 Johnsonville On-Ramp (S) VMS | 1N | All | 3 | Ramp closure | - | 2024-05-05 | 2024-05-05 | sure | - | - | - | Night | N | No
Wellington Transport Alliance (WTA) | WTA_ITS_23_80 Churton Park (S) VMS | 1N | All | 4 | Full closure/detour | - | 2024-05-05 | 2024-05-05 | sure | - | - | - | Night | N | No
Hawkes Bay TREC | Full road closure of SH2 between Links Road and Evenden Road, Closure is between 8pm to 5am (Night time only) | 2 | All Freight | 3 | Minor delays are expected along this route | Local detours will be in place for traffic, via Pakowhai Road and Evenden Rd, This route is suitable for most vehicles | 2024-05-05 | 2024-05-05 | sure | - | martin.colditz@trec.nz | - | Night | N | No
Bay of Plenty East | Rotorua Marathon - Running / Walking event around Lake Rotorua | 33 | All Freight | 3 | From 08:00 am to 05:00pm | Follow sign posted detours | 2024-05-04 | 2024-05-04 | +/- month | - | Wayne Hendrikse 027 341 1171 | murray@eventpromotions.co.nz | Day | N | No
Gisborne TREC | Asphalting programme - SH35 Hirini St to Crawford Road - NIGHT CLOSURE, DETOURS IN PLACE 1900hrs - 0500hrs | 35 | All freight | 4 | Closure with detour | Detours are being checked and agreed with the local authority | 2024-05-03 | 2024-05-12 | +/- a week | - | - | - | Night | N | Yes
North Canterbury | SH74 Lyttelton Tunnel Plaza - Resurfacing | 74 | All Freight | 3 | Stop / Go | - | 2024-05-02 | 2024-05-03 | +/- month | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | WTA - AWPT_23_03/04 Solway (South Belt - Derby St) - 747m | 2 | All | 4 | Minor delays | N/A | 2024-05-01 | 2024-05-30 | sure | Felicity Glynn | - | - | Night | N | No
West Coast | SH6 Ross to Hari Hari Tree Felling | 6 | All Freight | 4 | Open on the hour daytime stop/stops | No detour - Open on the hour | 2024-05-01 | 2024-05-07 | +/- 2 weeks | - | - | - | Day | N | No
Taranaki | SH3 - Awakino Gorge, culvert replacement | 3 | All Freight | 4 | No local road detour, days chosen considered low volume freight days. | No viable detour; clsoure period 10am-2pm; stop/go 7am- 10am and 2pm-6pm | 2024-04-30 | 2024-05-02 | +/- a week | - | - | - | Day | N | No
Hawkes Bay TREC | 40 Min Stop/Stops at Waione Bridge SH5, Ashphalt renewals and line marking | 5 | All Freight | 3 | 40 minute Stop/Stops at night at Waione Bridge on SH5 | No local Detour | 2024-04-30 | 2024-04-30 | sure | - | Martin Colditz | martin.colditz@trec.nz | Night | N | No
Wellington Transport Alliance (WTA) | TBC WTA_B_23_01 Tauherenikau Bridge repairs - NO HEAVY VEHICLES 24/7, full closure daytime weekdays for all vehicles | 53 | All | 3 | 24/7 full closure/detour | N/A | 2024-04-29 | 2024-06-04 | sure | david.cross@nzta.govt.nz | - | - | All | N | Yes
Gisborne TREC | Asphalting programme - SH35 Awapuni Road - NIGHT CLOSURE, DETOURS IN PLACE 1900hrs - 0500hrs | 35 | All freight | 4 | Closure with detour | Detours are being checked and agreed with the local authority | 2024-04-29 | 2024-05-02 | +/- a week | - | - | - | Night | N | Yes
Manawatu Whanganui | SH2 - Tamaki River Bridge CLOSURE 29 April - 4 May | 2 | All Freight | 4 | 24/7 Closure of SH2 at Tamaki River Bridge | NB detour Pinfold Road/Coppermine Road/Top Grass Road to Laws Road (10min detour) SB Detour Laws Road/Top Grass Road/Tamaki River Road ( <5mins detour) | 2024-04-29 | 2024-05-04 | +/- a week | - | Tiffanie Kanon | tiffanie.kanon@nzta.govt.nz | All | N | No
Nelson Tasman | SH6 Newton River Bridge - Full closure Structures - WSP/NOC | 6 | All Freight | 4 | Full Closure - Detour is via SH7 Reefton 50 MINS+ | SH65, SH7 and SH69 | 2024-04-29 | 2024-05-01 | sure | Claire.Fraser@nzta.govt.nz | - | - | All | N | No
Hawkes Bay TREC | Full Closure of SH5 in the night Between Glengarry Rd and Caroline Drive | 5 | All Freight | 4 | Full closure at night between Glengarry Rd and Caroline Drive on SH5 (8 PM to 5 AM) | No Local Detour | 2024-04-29 | 2024-04-29 | sure | - | Martin Colditz | martin.colditz@trec.nz | Night | N | No
Manawatu Whanganui | SH1 - Calico Line - 1 lane Closure; NB detour via heavy bypass route, SB thru site | 1 | All Freight | 3 | NB detour by heavy bypass route; Wings Line, French St, Matai St, Main St, Nga Tawa Rd, Calico. SB continues through the site. Monday to Friday; 8am - 5pm. | NB detour by heavy bypass route; Wings Line, French St, Matai St, Main St, Nga Tawa Rd, Calico. SB continues through the site. Monday to Friday; 8am - 5pm. | 2024-04-29 | 2024-05-08 | +/- a week | - | Aarin Bang | Aarin.Bang@nzta.govt.nz | Day | N | -
Wellington Transport Alliance (WTA) | WTA_AWPT_22_03/05 and TAC - SH2 Masterton Chapel St/Lincoln Rd - full directional road closures | 2 | All | 4 | Full closure/detour | N/A | 2024-04-28 | 2024-05-13 | sure | Felicity Glynn | - | - | Night | N | Yes
Central Waikato | SH01 - Mangatoetoe-nui bridge - Asphalting | 1N | All Freight | 4 | Night Road closure - 6:00pm to 6:00am closed at SH01 & 46 and Waiouru SH1 &49 | Detour for all vehicles - South bound from SH01 - right to SH46 left to SH47 left to SH04 left to SH49 back on to SH01 - Northbound visa versa | 2024-04-28 | 2024-04-29 | +/- a week | Melissa Elers | Ashley Green | Ashley@corridorsolutions.co.nz | Night | N | Yes
Bay of Plenty West | SH2 - Tasman Quay and Balance Cnr (Totara Street to Marina intersection) | 2 | All Freight | 3 | From 08:30pm to 05:30am - Road closure from Totara St to the Marina intersection | Detour via SH29A turning off at Bay Park ramp. Mt Maunganui bound traffic lanes will run as normal | 2024-04-28 | 2024-05-02 | +/- month | - | Downer | Wade.Thomas@downer.co.nz | Night | N | No
North Canterbury | SH75 Lillian St to Nicholls Rd - ANZAC Parade | 75 | All Freight | 3 | Closure with local detour | - | 2024-04-25 | 2024-04-25 | sure | - | - | - | Day | N | Yes
Gisborne TREC | Anzac Ceremonies 2024 | All | All Freight | 4 | delays | N/A | 2024-04-25 | 2024-04-25 | sure | - | - | - | Day | N | No
Gisborne TREC | ANZAC Ceremony 2024 - Gisborne Memorial with march over SH35 Gladstone Bridge | 35 | All Freight | 3 | Short duration closure of SH35 Gladstone Bridge as dawn service march across. | n/a | 2024-04-25 | 2024-04-25 | sure | - | GDC | - | Day | N | No
Wellington Transport Alliance (WTA) | SH2 Hebden Crescent - permanent closure of median access to/from northern access, left in left out access only | 2 | All Freight | 4 | Closure of right turn in and out of Hebden Cres | Detour via Manor Park Interchange with SH58 | 2024-04-22 | 2024-07-01 | +/- a week | David Cross | David Cross | sh2huttvalley@nzta.govt.nz | All | N | Yes
Wellington Transport Alliance (WTA) | WTA - median barriers KGB intersection - nighttime lane closures | 2 | All | 3 | Delays | - | 2024-04-22 | 2024-05-01 | sure | - | - | - | Night | N | Yes
Hawkes Bay TREC | * Proposed work* SH2 Waipawa, REHAB, Tamumu Road to Victoria Street | 2 | All Freight | 3 | Day time 6 AM to 4 PM, Waipawa Rehab Work. | - | 2024-04-22 | 2024-05-31 | +/- a week | - | Martin Colditz | martin.colditz@trec.nz | Day | N | No
Wellington Transport Alliance (WTA) | WTA_B_23_01 Tauherenikau Bridge repairs - full daytime closures with detour (contingency 24th) | 53 | All | 3 | Daytime full closure/detour | N/A | 2024-04-22 | 2024-04-23 | sure | david.cross@nzta.govt.nz | - | - | All | N | No
West Coast | SH73 McGraths Bridge (services trenching) | 73 | All Freight | 4 | Night Road closure 10pm - 2am | Detour via SH7 Lewis Pass & Reefton | 2024-04-22 | 2024-04-23 | sure | - | - | - | Night | - | No
Wellington Transport Alliance (WTA) | WTA_AWPT investigations work SH2 Masterton Chapel St/Lincoln Rd - nighttime closures | 2 | All | 3 | Full closure/detour | N/A | 2024-04-21 | 2024-04-25 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | TBC - SH1 Whakahoro southern end of bridge 24/7 stop/go Sun 8pm-Thurs | 1N | All | 3 | Delays | - | 2024-04-21 | 2024-04-25 | sure | - | - | - | All | N | No
Hawkes Bay TREC | Full road closure of SH2 between Evenden Road and Omahu Road, Closure between 8 pm to 5 am | 2 | All Freight | 3 | Minor delays are expected along this route | Local detours will be in place for light traffic, via Omahu Road, Ormond Road, and Evenden Rd HPMV Detour route, is Marekakaho Road, Pakowhai Road and Evenden Road | 2024-04-21 | 2024-04-21 | sure | - | Martin Colditz | martin.colditz@trec.nz | Night | N | No
West Coast | SH7 KiwiRail Crossing - Closure (not confirmed) | 7 | All Freight | 4 | Full Closure - Detour via State Highway 65/7 | Detour via SH69/6 | 2024-04-20 | 2024-04-22 | +/- Month | - | - | - | All | N | No
Central Waikato | V8 Supercars - Taupo Racetrack | 1N | All Freight | 3 | Delays due to high attendance event | Detour for light vehicles - Southbound - turn right on to Wiltsdown Rd, turn left onto Paraonui Rd Turn left onto Rollett Rd and back onto SH01 - Northbound via versa | 2024-04-19 | 2024-04-21 | sure | Matt Kofoed | - | - | All | N | No
Wellington Transport Alliance (WTA) | Mill and Pave WTA_SAL_23_11 Basin Reserve - access to/from Adelaide Rd closed from midnight, open by 04:00 | 1N | All | 3 | Access to Adelaide road closed | - | 2024-04-18 | 2024-04-19 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | WTA_SAL_23_04 - Dowse interchange to Melling northbound road closure 10pm-4am | 2 | All | 4 | Northbound full closure/detour | - | 2024-04-18 | 2024-04-19 | sure | - | - | - | Night | N | -
Hawkes Bay TREC | SH2 HB Expressway Full Road closure for Resurfacing Taradale Road roundabout | 2 | All Freight | 3 | 5 to 10 mins delay expected | Detour North Bound: Via the off ramp towards to Kennedy Road, SH51, Hyderabad Road, SH50. Rejoin SH2 at Prebensen Road roundabout South Bound: Via Prebensen roundabout to SH50, Hyderabad Road, SH51, Kennedy Road. Rejoin the HB Expressway at the Kennedy Road onramp | 2024-04-17 | 2024-04-19 | sure | - | Martin Colditz | martin.colditz@trec.nz | Night | N | No
North Canterbury | SH75 NZUP Halswell Rd - Curletts Rd to Dunbars Dr - Widening and intersection upgrades | 75 | All freight | 4 | Generally maintaining two lanes on Halswell Rd during the day under lane diversions and temporary controls. Sideroad closures/restrictions. Single-lane Stop/Go control overnights | Generally no detours anticipated for SH75 traffic. Overdimension loads wishing to pass through the worksite must coordinate with the project team in advance | 2024-04-15 | 2026-04-01 | +/- 2 weeks | - | Fulton Hogan - contact details TBC | - | All | N | Yes
Hawkes Bay TREC | SH5 Ellis Wallace Rd Safety improvement | 5 | All Freight | 3 | Multiple safety improvement site on SH5 under stop/Go especting 10 to 15 minutes delay. | - | 2024-04-15 | - | sure | - | Martin Colditz | martin.colditz@trec.nz | Day | N | Yes
Coastal Otago | SH1, Waikouaiti 01S-0651/13.965 - 01S-0651/12.900 | 1S | All Freight | 3 | Single lane closure with MTC/PTS with 30 TSL | N/A | 2024-04-15 | 2024-04-26 | sure | - | Downer 0800 44 44 49 | coastalotago@downer.co.nz | All | - | Yes
Wellington Transport Alliance (WTA) | WTA_P_24_02 Wards Line slip remediation emergency works + Bidwills Cutting shoulder widening & barrier installation - daytime stop/go | 53 | - | 3 | Delays | - | 2024-04-15 | 2024-05-30 | sure | - | - | - | Day | N | No
Bay of Plenty East | SH2 - Pekatahi Bridge | 2 | All Freight | 3 | From 08:30am to 04:30pm there will be a full road closure in place between Rewatu Rd and Taneatua Rd with no access over the bridge. | Traffic heading North on SH2, turn right onto Taneatua Rd towards Whakatane, continue onto Valley Rd, turn left onto Arawa Rd, continue onto Hinemoa St, take 2nd exit onto SH30, continue onto SH2 and SH30 intersection at Awakeri, and vice versa. Traffic heading South on SH2, continue straight onto SH30 towards Whakatane, continue onto Hinemoa St (towards hospital), continue straight onto Arawa Rd, turn right onto Valley Rd, continue onto Taneatua Rd and SH2 intersection, and vice versa. Traffic heading East from Foster Rd, turn left onto SH2 northbound, and follow Southbound detour route outlined above. | 2024-04-15 | 2024-04-19 | +/- a week | - | Schevonne Spies | S.Spies@higgins.co.nz | Day | Y | -
North Canterbury | SH77 Homebush Rd - West of Route 72 - Twin Armco Culvert replacement | 77 | All Freight | 4 | Full Closure 15-19 April and 22-24 April with local detour suitable for light vehicles, general access (44T), 50MAX and HPMV permitted vehicles. Stop / Go control 20-21 and 25-28 April. | The primary detour route is: Telegraph, Bealey, and Coalgate Rds. An advance detour route onto Bealey Rd commences at Aylesbury for SH73 westbound traffic. | 2024-04-15 | 2024-04-24 | sure | - | Southernlink Canterbury NOC | Rosemary Annandale 0274312151 Rosemary.Annandale@downer.co.nz | All | N | -
Bay of Plenty East | SH30 - Taahunaatara Bridge repairs | 30 | All Freight | 3 | Shoulder closure Monday and Tuesday and lane closures on Wednesday, Thursday and Friday. Traffic lights will be in place. | N/A | 2024-04-15 | 2024-04-19 | +/- a week | - | Maxbuild | gary@maxbuild.co.nz | All | N | -
Wellington Transport Alliance (WTA) | SH2 Featherston, Daniell St stormwater pipe replacement - nighttime full closures | 2 | - | 4 | Full closure/short detour | - | 2024-04-14 | 2024-04-23 | sure | - | - | - | Night | N | Yes
Wellington Transport Alliance (WTA) | WTA SH2 Remutaka Hill 5 Night Closure - April - Sun-Thur nights | 2 | All | 4 | Closure with long detour | Long Detour (aprox 2hrs) via Pahiatua | 2024-04-14 | 2024-04-19 | sure | Felicity Glynn | Lisa Henderson | asheesh.chand@wta.nzta.govt.nz | Night | N | Yes
Taranaki | SH4 - Taumarunui April/May 2024 - Ashphalt renewal | 4 | All freight | 3 | NB closure with <5min detour via Turaki St, Miriama St & River Rd | NB detoured via Turaki Street, Miriama Street and River Road, SB remain on SH4 | 2024-04-14 | 2024-05-01 | +/- a week | - | - | - | Day | N | No
Bay of Plenty West | SH2 - Z Petrol Station (Hewletts Flyover westbound closure - Aerodrome Road to Jean Batten Drive) | 2 | All Freight | 3 | From 08:30pm to 05:30am road will be closed from Hewletts Flyover (westbound lanes), Aerodrome Road to Jean Batten Drive for resurfacing works. Closure dates: 14/04/24-18/04/24; 21/04/24-23/04/24 | Follow signposted detours | 2024-04-14 | 2024-04-23 | +/- 3 weeks | - | Downer | Wade.Thomas@downer.co.nz | Night | N | No
Central Otago | SH6 Drainage night works on Kawarau Gorge | 6 | All Freight | 3 | ROAD CLOSURE opening on the hour ever hour – no detour | N/A | 2024-04-14 | 2024-04-19 | +/- a week | - | Traffic Management – Gary Speak Gary.speak@fultonhogan.com Contractor – Sam Gillaly Sam.gillaly@fultonhogan.com | Gary – 027 275 1632 Sam – 027 246 2492 | All | N | No
Wellington Transport Alliance (WTA) | WTA_TAC_22_54 & WTA_TAC_22_55 Tinakori Rd NB Off-Ramp | 1N | All | 3 | Ramp closure | - | 2024-04-14 | 2024-04-19 | sure | - | - | - | Night | N | -
Bay of Plenty West | Links Avenue (Mount Maunganui) - Full closure by Tauranga City Council | 2 | - | 4 | Works to take place from 06:00am to 10:00pm. Overnight site monitoring to be place. Residential access only. Follow signposted detours. | Residential access only. Follow signposted detours. | 2024-04-13 | 2024-04-28 | Sure | - | Tauranga City Council | info@tauranga.govt.nz | All | N | No
Gisborne TREC | Asphalting programme - SH2 Jolly Stockman - Stop / Go 6PM - 6AM | 2 | All freight | 3 | Delays due to stop go | - | 2024-04-11 | 2024-11-04 | +/- a week | - | - | - | Night | Y | No
Bay of Plenty East | SH2 Waioeka Gorge - Oponae underslip repair works | 3 | Over Dimension | 3 | Maximum lane width during day-time working hours of 3 metres. Working hours 7am-6pm. OD loads to call ahead of time to advise of intended movement | Stop/stop traffic managment will be in place. Expect up to 30 minute delays. | 2024-04-08 | 2024-04-24 | +/- a week | - | - | frankie.evans@nzta.govt.nz | Day | N | No
East Waikato | SH2 - Karangahake Gorge FULL NIGHTIME CLOSURES APRIL | 2 | All Freight | 4 | Road closed between 8.00pm and 6.00am for 4 nights. Alternative route required |  | 2024-04-07 | 2024-05-01 | sure |  | Ali Ayoubi | ewnoc@higgins.co.nz | Night | N | No
Auckland System Management (ASM) | Commercial Vehicle Safety Programme - SH16 Symonds Street | 16 | All Freight | 3 | Night works - SH6 eastbound Pork link closed from SH1 southbound and SH16. Follow signposted detour. | From SH1 southbound -exit at Fanshawe Street and reenter at Hobson Street. SH1 to SH16 - exit at Fanshawe Street and follow detour via Customs Street East and Beach Road SH16 eastbound to Port: Take SH1 SB Hamilton, exit at Gillies Ave and reenter at Gillies Ave northbound on-ramp. Take SH1 northbound link to Ports | 2024-04-04 | 2025-01-01 | +/- a week | - | - | - | Night | N | No
Southland | SH1 Clyde Street between Nith Street and Earn Street on | 1S | All Freight | 3 | SH1 Clyde St Southbound closed between Earn and Nith St. SH1 Clyde St Northbound closed at Bond St | Southbound (All Vehicles): Left onto Earn St, Right onto Nith St, down to SH1. Southbound HCVs on Bond St pybass:Left onto Annan St, Right onto Crinan St through to SH1 Clyde St, right onto Clyde St, (then use detour as above) Northbound (Light Vehicles): Left onto Bond St, then either onto Annan St to Crinan St or follow Bond St out onto Tweed Nothbound HCVs: Unaffected, use Bond St bypass | 2024-04-03 | 2024-05-03 | sure | - | 212409314 | - | All | N | No
Gisborne TREC | SH35 Hikuwai Bridge Replacement Construction (17km North of Tolaga Bay) | 35 | All Freight | 3 | Some additional truck movements and delays on route | n/A | 2024-04-02 | 2026-01-01 | sure | - | - | - | All | N | No
Central Otago | SH6 Bungy rock bolting and meshing around Kawarau bridge | 6 | All Freight | 3 | SINGLE LANE CLOSURE: from Tuesday 2nd April at 9am to 7th May 2024 at 4pm STOP/GO in place and expect up to 10 minutes delays. TSL 30km/ph STOP/STOP may also operate at times depending on rock fall, expect up to 15 minute delays should this occur. 0900 – 1600 Daily | N/A | 2024-04-02 | 2024-05-07 | +/- 2 weeks | - | Gary – 027 275 1632 Clinton – 0275533346 | Traffic Management – Gary Speak Gary.speak@fultonhogan.com Contractor – Clinton Beavan Clinton.Beavan@fultonhogan.com | Day | N | No
Wellington Transport Alliance (WTA) | WTA - median barriers B1001 under Petone OB - nighttime lane closures both directions, occasional directional full closures in May | 2 | All | 3 | Delays | - | 2024-04-02 | 2024-05-04 | sure | - | - | - | Night | N | No
Wellington Transport Alliance (WTA) | WTA - side barriers B2032/2033 KGB intersection - nighttime lane closures | 2 | All | 3 | Delays | - | 2024-04-02 | 2024-05-04 | sure | - | - | - | Night | N | No
Central Otago | SH6 Scaling works Kawarau Gorge | 6 | All Freight | 3 | 10 min delays for Rock scaling works to be completed, under StopGO operation, with manually operated Trafic Lights | n/a | 2024-04-02 | 2024-05-03 | +/- 2 weeks | - | Clinton Beavan | Clinton.Beavan@fultonhogan.com | Day | N | No
North Canterbury | SH75 Railway Iron Corner - underslip toe protection and releveling | 75 | All Freight | 3 | Stop / Go - up to 15 min closures. Coordination with Guardrail improvement project | - | 2024-04-02 | 2024-04-23 | +/- Month | - | Southernlink Canterbury NOC | Rosemary Annandale 0274312151 Rosemary.Annandale@downer.co.nz | Day | N | No
North Canterbury | SH1 Burnham Rd to Thompsons Rd - Project potholing | 1S | All Freight | 3 | Stop / Go | - | 2024-04-02 | 2024-04-20 | +/- Month | - | - | - | Night | N | No
Taranaki | SH3 - Mt Messenger - Stop/GO 2nd-4th April 8th-19th April | 3 | All Freight | 3 | Expect delays of <20mins, no viable detour available | Expect delays of <20mins, no viable detour available | 2024-04-02 | 2024-04-19 | sure | - | Mike Dickson | Mike.Dickson@nzta.govt.nz | Night | N | No
West Waikato | SH1C Te Rapa Expressway Asphat resurfacing renewal site. Starts at Waiere Drive interchange and ends at the Horotiu interchange and includes the entire Te Rapa expressway | 1C | All Freight | 5 | Time delays | Lane deviations in place and periodic ramp closures | 2024-04-01 | 2024-06-30 | +/- 2 weeks | - | Glenys Farries | glenys.farries@fultonhogan.com | All | N | No
Marlborough Roads | SH1 Picton Elevation Stage 2 (Culvert resconstruction) | 1S | All Freight | 4 | 6pm - 6am Delays 15 mins - Northbouond ferry traffic prioritised | - | 2024-03-25 | 2024-05-01 | sure | - | - | - | Night | N | No
Gisborne TREC | SH2 Oliver Road - Nth of Otoko Hill Area - LIKELY Foam Stabilisation Works - 24hrs Stop Go | 2 | All Freight | 3 | 24 hrs Stop Go, managed flows | - | 2024-03-25 | 2024-04-22 | +/- 2 weeks | - | - | - | All | N | No
North Canterbury | SH75 LCLR Little River Shared User Path - Construction | 75 | All Freight | 3 | Lane diversion and 30kph TSL. Possibly intermittant Stop/Go | - | 2024-03-25 | 2024-05-21 | +/- 6 months | - | - | - | Day | N | -
Auckland System Management (ASM) | Commercial Vehicle Safety Programme - SH1 Grafton Rd Bridge | 1N | All Freight | 3 | Night works - SH1 to SH16 eastbound link closed. Follow signposted detour from SH1 Symonds St | Symonds Street and Grafton Road to SH16 Stanley Street | 2024-03-24 | 2025-01-01 | sure | - | - | - | Night | N | No
West Coast | SH65 Deep Gully Culvert Replacement | 65 | All Freight | 4 | Road Closure 6am - 6.30pm (hour opening 1230-130) | Detour via SH7 Reefton | 2024-03-19 | - | sure | - | - | - | Day | - | No
Auckland System Management (ASM) | O Mahurangi (Penlink) - SH1 Northern Motorway Night Works | 1N | All Freight | 3 | Night works - NB road closed | East Coast Road | 2024-03-15 | 2024-04-22 | sure | - | - | - | Night | N | No
North Canterbury | SH1 Waipapa Bay and Polo Fields - AWT | 1S | All Freight | 3 | Stop / Go | - | 2024-03-12 | 2024-04-26 | +/- Month | - | Southernlink Canterbury NOC | Rosemary Annandale 0274312151 Rosemary.Annandale@downer.co.nz | All | N | No
North Canterbury | SH1/73 Russley/Yaldhurst Intersection - Signal pole replacement | 1S | All Freight | 3 | Lane Closures and Heavy Vehicle Turn Restrictions | - | 2024-03-10 | 2024-04-22 | +/- Month | - | - | - | Night | N | No
Gisborne TREC | SH35 Maraetaha - Slow Vehicle Bay Extension - Stop/Go Signals Mon - Sat 6am to 7pm | 35 | All Freight | 3 | Up to 15 Minutes delay | - | 2024-03-06 | 2024-06-01 | sure | - | - | Courtney.Henderson@nzta.govt.nz | All | N | No
Nelson Tasman | SH6 Whangamoa Forestry Operations | 6 | All Freight | 3 | Delays 10 minute stop stops | - | 2024-03-04 | 2024-05-31 | sure | - | - | - | Day | - | No
West Waikato | SH1C - Hamilton urban, Norton Road roundabout improvements | 1C | - | 3 | - | - | 2024-03-01 | 2024-06-30 | sure | Matt Kofoed | Glenys Farries | west.waikato@fultonhogan.com | All | N | No
Marlborough Roads | Grape Harvest (Mainly SH1 SH6 and SH63) 2024 | 1S | All Freight | 3 | Minimise our delays due to Grape Harvest | - | 2024-03-01 | 2024-04-30 | +/- a week | - | - | - | All | N | No
Northland | Recovery Site - SH1 Brynderwyn Hills (Full Closure) | 1N | All Vehicles | 4 | No trucks with trailers on cove road detour. No HPMV higher mass on Paparoa Oakleigh. | Detours via Paparoa Oakleigh, or SH12/14 | 2024-02-26 | 2024-05-12 | sure | - | - | - | All | N | No
South Canterbury | SH1 Ealing Rehab (Stop go @ night) | 1S | All Freight | 3 | Stop/Go or detour in place (Delays up to 30 mins possible) | - | 2024-02-24 | 2024-04-26 | +/- a week | TBC | - | - | Night | N | No
North Canterbury | SH75 LCLR Cooptown to Hilltop - Guardrail improvements | 75 | All freight | 3 | Stop / Go - up to 15 min closures | - | 2024-02-14 | 2024-05-31 | +/- 3 months | - | Schick - Kenny Starr | 021 197 2772 kenny.starr@schick.co.nz | All | N | Yes
North Canterbury | SH75 Hendersons Rd - Watermain install | 75 | All freight | 3 | Stop / Go | - | 2024-02-12 | 2024-04-26 | +/- 3 months | - | - | - | All | N | No
Coastal Otago | SH1, Moeraki 01S-0618/14.466 - 01S-0618/10.977 | 1S | All Freight | 3 | Intersection upgrades, 3-way stop/go and temporary speed restrictions ath the intersection of SH1 and Hillgrove-Moeraki Road. Day shift 7am-5pm | n/a | 2024-02-07 | 2024-04-26 | sure | - | Downer 0800 44 44 49 | coastalotago@downer.co.nz | Day | N | Yes
Southland | Riverton ANZAC Parade | 99 | All Freight | 3 | SH99 Closed between Princes St and Jetty St as Parade moves East, SH99 closed between Jetty St and Bay Rd to allow parade to cross Aparima river Bridge | Westbound on SH99: Left onto Princess St, right onto Havelock St, right onto Jetty St, left onto SH99 Eastbound on SH99: Reverse of above. | 2024-04-25 | 2024-04-25 | sure | Maja Katavic Michael Weusten | 022 430 5269 027 230 9410 |  | Day
Southland | Bluff Shared Use Path | 1S | All Freight | 3 | Temporary Signals at the SH1S(Ocean Beach road) Suir st, Blackwater st intersection. Temporary signals at the SH1S (Blackwater st) Shannon st intersection. | N/A | 2024-02-07 | 2024-05-10 | sure | - | 272757393 | - | All | N | No
West Coast | SH73 McGraths Bridge - strengthening | 73 | All | 3 | Possible long site stop/go | - | 2024-02-01 | 2024-06-10 | sure | TBC | - | - | Day | N | No
North Canterbury | SH1 LCLR Tram Rd Off-ramp - Signalisation and Safety Improvements | 1S | All Freight | 3 | Overnight closures of the Off-Ramp and Tram Rd. One-way system on Tram Rd mwy overbridge (Westbound closed, Eastbound open). No Right Turn from Off-Ramp during some stages of work. Overdimension loads wishing to pass through the worksite must coordinate with the project team in advance | - | 2024-01-29 | 2024-04-28 | +/- 3 months | - | Signal Civil - Jon Field | jon@signalcivil.co.nz | All | N | Yes
Auckland System Management (ASM) | SH 16 Te Atatu EB on ramp widening | 16 | All Freight | 3 | Widening works will result in various restrictions with the on ramp. Night works will close EB on ramp with detour in place. Spiral on ramp will remain open. Majority of works are day works across two phases. First stage: After morning peak, T2/freight lane will close until early evening. Two general traffic lanes remain open. Second stage: T2/freight lane closed 24/7. One general traffic lane open. Looking for works to be completed over a two week period. At this time The Te Atatu Rd T3/freight lane and right turn onto the on ramp will be closed and a detour in place. Sprial on ramp remains fully open. | - | 2024-01-28 | 2024-05-15 | +/- a week | - | - | - | All | N | No
Wellington Transport Alliance (WTA) | M2C Norfolk/Cornwall RAB, Wiltons RAB - NB/SB one-way closures as required for finishing works | 2 | - | 3 | Delays and potential closures/detours | - | 2024-01-25 | 2024-04-30 | sure | - | - | - | Night | N | No
Central Waikato | SH01 - ETA Safety Improvement Project | 1N | All Freight | 3 | contraflow with speed restriction | - | 2024-01-24 | 2024-06-25 | sure | - | James Waerea | james@tupore.co.nz | All | N | No
Marlborough Roads | SH6 SIP Roundabout Construction - Bells / St Leonards (westbound closure) | 6 | All Freight | 4 | Westbound closure - local detour / 5-10 mins | - | 2024-01-15 | 2024-06-01 | sure | - | - | - | All | N | No
Gisborne TREC | SH35 Mangahauini Gorge (major scour site) | 35 | All freight | 3 | Delays due to stop go operation | - | 2024-01-10 | 2026-01-01 | sure | - | - | - | All | N | No
Bay of Plenty West | SH29/SH2 Takitimu North Link Stg 1 - Moffat Road closure | 29 & 2 | All | 3 | Detour via SH29 TDTR for heavy vehicles | n/a (SH29A available) | 2024-01-09 | 2024-04-30 | +/- 3 months | - | Lateef Fadun | - | All | N | No
North Canterbury | SH76 Brougham St - Orion Milton to Bromley 66kV Cable - Stages 5-7 Waltham to Burlington and Joint Bays (jointing) | 76 | All freight | 3 | Turn-lane closures and 30kph TSL continuously. Lane closures, intersection restrictions and contraflow operations at night | - | 2024-01-08 | 2024-05-31 | sure | - | Isaac Construction | 66kVbromleytomilton@isaac.co.nz | All | N | No
East Waikato | SH26 - FULL CLOSURE Onetai bridge replacement | 26 | All Freight | 4 | full closure for 7 days | - | 2024-01-05 | 2024-06-30 | sure | Matt Kofoed | Ali Ayoubi | ewnoc@higgins.co.nz | All | N | No
Manawatu Whanganui | SH1 SIP - SH1 / 57 Roundabout | 1N | - | 4 | - | - | 2024-01-01 | 2025-01-01 | sure | - | Ralph Parkes | ralph.parkes@nzta.govt.nz | All | N | No
Hawkes Bay TREC | SH2 Devils Elbow Cyclone Recovery Project | 2 | All freight | 3 | delays | - | 2023-12-01 | 2025-01-01 | sure | - | - | - | all | N | No
Wellington Transport Alliance (WTA) | Riverlink - Lower Hutt/Melling Project | 2 | All | 3 | Varying closures and delays during some stages of the project | N/A | 2023-11-01 | 2027-06-01 | sure | - | - | - | All | N | No
West Waikato | SH3 Ohaupo Village Pedestrian Safety Improvements | 3 | All Freight | 3 | Lane diversion and stop/go | - | 2023-10-25 | 2024-04-26 | sure | - | Glenys Farries | west.waikato@fultonhogan.com | All | N | No
Central Waikato | SH01 - Atiamuri to Wairakei, Package N (Maroa) repairs | 1N | - | 3 | - | - | 2023-10-23 | 2024-06-30 | sure | - | - | - | All | N | No
North Canterbury | SH75 Candys Rd - Roundabout construction + SUP (LCLR contribution) | 75 | All freight | 3 | Stop / Go between 7am and 6pm, Temporary road | - | 2023-09-14 | 2024-04-26 | +/- 3 months | - | Schick - John Flower | - | All | N | No
Gisborne TREC | SH35 Hikuwai Bailey Bridge (17km North of Tolaga Bay) Restrictions | 35 | All Freight | 3 | 10km/h Speed Restriction. 50 Max permitted, HPMV not permitted, Over weight- By permit only | n/A | 2023-06-14 | 2026-01-01 | sure | - | - | - | All | N | No
Manawatu Whanganui | SH1 SIP - Levin to Foxton (North of Levin) - Expect detours on SH1 | 1N | - | 3 | Delays and possible detours | - | 2023-04-01 | 2025-08-01 | +/- Month | - | - | - | All | N | No
South Canterbury | SH1 Showgrounds Development - Grants Road Timaru | 1S | all | 3 | Delays | - | 2023-04-01 | 2024-05-01 | +/- a week | TBC | - | - | All | N | No
Hawkes Bay TREC | SH2 Waikare River Bailey Bridge (1km West of Putorino) Restrictions | 2 | 50 Max permitted HPMW not permitted Over weight- By permit only | 3 | 10km/h Speed Restriction. 50 Max permitted, HPMV not permitted, Over weight- By permit only | No Viable Detour Available | 2023-03-01 | 2025-01-01 | sure | - | - | - | All | N | No
Central Waikato | SH41 - underslip - Waihi - down to one lane | 41 | All Freight | 3 | Down to one lane - under traffic lights with temporary speed restrictions | - | 2023-02-08 | 2026-01-01 | sure | - | Tux Gallagher | Takerei.Gallagher2@downer.co.nz | All | N | No
Nelson Tasman | SH60 Ruby Bay Median Barrier (SIP project) | 60 | All Freight | 4 | Contraflows | No | 2023-02-07 | 2024-07-01 | sure | Claire.Fraser@nzta.govt.nz | - | - | All | N | No
East Waikato | SH25A Kopu to Hikuai | 25A | All Freight | 4 | - | - | 2023-01-31 | 2025-01-01 | sure | - | Ali Ayoubi | ewnoc@higgins.co.nz | All | N | No
West Waikato | SH1 - Rangiriri Section, Rangiriri final surfacing | 1N | - | 3 | - | - | 2023-01-11 | 2024-04-30 | sure | Matt Kofoed | Glenys Farries | west.waikato@fultonhogan.com | All | N | No
Hawkes Bay TREC | SH50 Ngaruroro River Bridge (Fernhill) Weight Restriction | 50 | All freight | 3 | Various weight restrictions, based on axel configuration. Contact permitting officer. | - | 2023-01-01 | 2025-01-01 | sure | - | - | - | All | N | No
Bay of Plenty West | SH2 TELTR - Rangiuru interchange construction - (Third Party Project) | 2 | All | 3 | Lane closures in place - possible time delays. Occaisonal overnight closures to be communicated ahead of time. | n/a | 2023-01-01 | 2024-12-01 | +/- 3 months | - | John McCarthy | - | All | N | No
West Waikato | SH1 - Cambridge to Piarere, Karapiro Safety Improvements | 1N | - | 3 | - | - | 2022-12-01 | 2024-12-31 | sure | Matt Kofoed | Glenys Farries | west.waikato@fultonhogan.com | All | N | No
West Waikato | SH1 - FULL CLOSURES Ngaruawahia Section, Ngaruawahia section pavement repairs | 1N | All Freight | 3 | Closures, HPMV and overweight vehicles to detour | Northbound closures: 11-22 February, Sunday to Thursday, 7pm-5am. HPMVs must use SH1B, and overweight vehicles need to use SH2/27, under an existing overweight permit. Southbound closures: 25 February to7 March, Sunday to Thursday, 7pm-5am. Heavy vehicles (50 tonnes and above) must continue on SH1B, including the local road detour around Telephone Road, and connect to SH1 again at Cambridge or via SH26 into Hamilton | 2022-10-31 | 2025-06-30 | sure | Matt Kofoed | Glenys Farries | west.waikato@fultonhogan.com | All | N | No
Taranaki | SH3 - Mt Messenger - Project | 3 | - | 3 | Delays | - | 2022-10-01 | 2027-01-01 | +/- 6 months | - | - | - | All | N | No
Bay of Plenty West | SH2 TELTR Papamoa Eastern Interchange construction- (Third Party Project) | 2 | All | 3 | Lane closures in place - possible time delays. Occaisonal overnight closures to be communicated ahead of time. | - | 2022-07-01 | 2026-07-01 | +/- 6 months | - | - | - | All | N | No
Bay of Plenty West | SH2/SH29A Bay Link (Bayfair to Baypark) grade separation project. | 2 | All | 3 | Time delays | - | 2018-01-01 | 2024-06-30 | +/- 3 months | - | Paul Willey | - | All | N | No

## Instructions
INSTRUCTIONS
Colour Coding for Main Register amendments
| REGION (add extra rows when needed) | PROJECT NAME | SH | RS/RP OR LOCATION | Vehicle Type affected (Over Dimension, HPMV, 50Max, all frieght) | STATUS (use dropdown) | RESTRICTION DESCRIPTION
Amended Row (See Status field) | Auckland | ShX - Bill Creek Hollow | X | 1023/23.12 | HPMV | In Design | HPMV Vehicle will be required to use the 2.3km detour route, which is likely to add 5minutes to their journey
New Row Add (all fields) | Northland | SHz - Dome Hill Improvements | Z | Between Hillworth and Wells | All Vehicles | In Construction | All over dimension loads will need to use the SHz route
Removed Row | Wellington | SHs - Happy Valley Drop out | s | Happy Valley River Bridge | Over Dimension | Planned | Width restriction on 10metres
Colour coding to be added for a week and then removed.

## Look-Ups
Planned
In Design
In Construction