## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Group Phase | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR
2017-04-13 | April 2017 Review | New approval | Walking and cycling improvements | Cycling facilities | Auckland Transport | Auckland Cycle Network - City Centre Network | Implementation | UCP - ACN CCN - Tamaki Drive (Seg 1/3) IMP (NLTF) | HH5.1 | HH5+ | N | 1 | Approved with conditions precedent | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Investment Transport online or by request | 2913817 | 1486047 | Auckland Transportâ€™s Chief Financial Officer provides written confirmation that all relevant consents have been obtained for segment one; and Auckland Transportâ€™s Chief Financial Officer provides written confirmation that Auckland Transport acknowledges that the NLTF contribution for the implementation cost of segment one is capped at $1.49 million. | 5.1 | 0 | 6.8
2017-04-13 | April 2017 Review | New approval | External funding | Cycling facilities | Auckland Transport | Auckland Cycle Network - City Centre Network | Implementation | UCP - ACN CCN - Tamaki Drive (Seg 1/3) IMP (UCF) | HH5.1 | HH5+ | N | 1 | Approved with conditions precedent | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Investment Transport online or by request | 870000 | 870000 | Auckland Transportâ€™s Chief Financial Officer provides written confirmation that all relevant consents have been obtained for segment one; and Auckland Transportâ€™s Chief Financial Officer provides written confirmation that Auckland Transport acknowledges that the NLTF contribution for the implementation cost of segment one is capped at $1.49 million. | 5.1 | 0 | 6.8
2017-04-26 | April 2017 Review | New approval | State highway maintenance | Emergency works | Northland Highway & Network Operations | EW Auckland North 12-3-17 Storm Event | Construction |  | ___ |  | Y | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 374525 | 374525
2017-04-11 | April 2017 Review | New approval | Local road maintenance | Emergency works | Ruapehu District Council | Ruapehu Event 12 Mar 17 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 240000 | 156000
2017-04-11 | April 2017 Review | New approval | State highway maintenance | Emergency works | Wellington Highway & Network Operations | E/W Nov 2016 EQ WLG Structure Repair | Construction |  | ___ |  | Y | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 557500 | 557500
2017-04-18 | April 2017 Review | New approval | State highway maintenance | Emergency works | Wellington Highway & Network Operations | E/W Wellington-November 2016 EQ & Storm | Construction |  | ___ |  | Y | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 3322947 | 3322947
2017-04-07 | April 2017 Review | New approval | Local road maintenance | Emergency works | Westland District Council | Jackson Bay Road. Land subsidance event 1 Feb 2017 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 110000 | 110000
2017-04-13 | April 2017 Review | New approval | Local road improvements | New traffic management facilities | Timaru District Council | Level Crossing Upgrade projects | Construction | Eversley Street rail crossing upgrade | HM99 | HM5+ | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 65000 | 65000 |  | 99 | 99 | 99
2017-04-13 | April 2017 Review | New approval | Local road improvements | New traffic management facilities | Timaru District Council | Level Crossing Upgrade projects | Construction | Arundel Belfield road/rail crossing | HM99 | HM5+ | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 120000 | 120000 |  | 99 | 99 | 99
2017-04-03 | April 2017 Review | New approval | External funding | Property purchase (State highways) | Canterbury Highway & Network Operations | Kaikoura Nov 2016 EQ: SH1 between Clarence & Oaro (Crown | Property | Property | HH1.5 | HH5+ | Y | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1026000 | 1026000 |  |  | 1.5 | 1.5
2017-04-19 | April 2017 Review | New approval | Public transport | Public transport improvements, major renewals and minor improvements | Auckland Transport | Station Level of Service Improvements A | Implementation |  | HH1.9 | HHL* | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 13980000 | 7129800 |  |  | 1.9 | 0.6
2017-04-26 | April 2017 Review | New approval | Public transport | Public transport improvements, major renewals and minor improvements | NZ Transport Agency | Mobility as a Service â€“ Pilot (Queenstown/Auckland Airport | Detailed Business Case | DBC/Pilot - design and testing of proof of concept | HM0 | HM1* | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 3100000 | 3100000 |  |  | 0 | 0
2017-04-10 | April 2017 Review | New approval | Public transport | Public transport information supply, operations and maintenance | NZ Transport Agency | Mobility as a Service â€“ Pilot (Queenstown/Auckland Airport | Detailed Business Case | DBC/Pilot | HM0 | HM1* | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 3100000 | 3100000 |  |  | 0 | 0
2017-04-19 | April 2017 Review | New approval | Regional Improvements | Replacement of bridges and other structures | Waikato Highway & Network Operations | SH27 Mangawhero Bridge | Detailed Business Case | Single Stage Business Case | HM3.1 | HM1-2.9 | Y | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 311093 | 311093 |  | 3.1 | 0 | 3.1
2017-04-20 | April 2017 Review | New approval | State highway improvements | Resilience improvements | Northland Highway & Network Operations | SH12 Dakers Culvert Flooding Mitigation | Implementation |  | HHM | HHM | Y | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 375000 | 375000
2017-04-20 | April 2017 Review | New approval | State highway improvements | Resilience improvements | Northland Highway & Network Operations | SH12 Rotu Culvert Flooding Mitigation | Implementation |  | HHM | HHM | Y | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 540915 | 540915
2017-04-20 | April 2017 Review | New approval | State highway improvements | Resilience improvements | Northland Highway & Network Operations | SH1N Callaghan Rd | Implementation |  | HHL | HHL | Y | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 580716 | 580716
2017-04-26 | April 2017 Review | New approval | Local road improvements | Road improvements | Auckland Transport | RSP-Great North/Bullock Track/Tuarangi Rds Intersectn Improv | Implementation | Gt Nth / Bullock / Tuarangi - Imp | HH.8 | HH1-2.9 | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1701000 | 867510 |  | 0.8 | 0.8 | 0.8
2017-04-12 | April 2017 Review | New approval | Regional Improvements | Road improvements | Canterbury Highway & Network Operations | Kaikoura Nov 2016 EQ: Lewis Pass Altern Upg Rout - Canterbur | Implementation | Implementation | HM1.4 | HM1-2.9 | Y | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 14979600 | 14979600 |  | 1.4 | 1.4 | 1.4
2017-04-19 | April 2017 Review | New approval | Local road improvements | Road improvements | Dunedin City Council | Puddle Alley and Dukes Rd Intersection Upgrade | Implementation | Implementation | HH3 | HH3-4.9 | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 700000 | 406000 |  | 3 | 3 | 3
2017-04-26 | April 2017 Review | New approval | Regional Improvements | Road improvements | Gisborne Highway & Network Operations | HPMV T2 Gis HNO Te Araroa to Tologa | Implementation |  | MH1.8 | MMM | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1539000 | 1539000 |  |  | 1.8 | 1.8
2017-04-26 | April 2017 Review | New approval | Regional Improvements | Road improvements | Hawkes Bay Highway & Network Operations | HPMV T2 HB HNO Napier Port to South Boundry | Implementation |  | HHM | HHM | Y | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 2237476 | 2237476 |  |  | 2 | 2
2017-04-13 | April 2017 Review | New approval | Local road improvements | Road improvements | Hurunui District Council | Kaikoura Nov 2016 EQ: route 70 improvements HDC | Implementation | Implementation | HM1 | HM1-2.9 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 5000000 | 5000000 |  | 1 | 1.4 | 1.4
2017-04-13 | April 2017 Review | New approval | Local road improvements | Road improvements | Kaikoura District Council | Kaikoura Nov 2016 EQ: route 70 improvements KDC | Implementation | Implementation | HM1 | HM1-2.9 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 5000000 | 5000000 |  | 1 | 1.4 | 1.4
2017-04-07 | April 2017 Review | New approval | Local road improvements | Road improvements | NZ Transport Agency | Safer Journeys Implementation plan to 2020 | Pre-implementation* |  | HM0 | HM1* | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 300000 | 300000 |  |  | 0 | 0
2017-04-12 | April 2017 Review | New approval | State highway improvements | Road improvements | Northland Highway & Network Operations | SH1 - Port Marsden Highway to Te Hana | Detailed Business Case | Single stage IBC/DBC | HH.9 | HH1* | N | 3 | Approved with conditions | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Investment Transport online or by request | 3250000 | 3250000 | subject to, as conditions subsequent, hold points after the development of a short-list of options for each section to provide assurance to the VAC that the short-lists have been developed following an appropriately robust process. |  | 0.9 | 0.9
2017-04-12 | April 2017 Review | New approval | State highway improvements | Road improvements | Northland Highway & Network Operations | SH1 - Whangarei to Port Marsden Highway | Detailed Business Case | Single stage IBC/DBC | HH1.1 | HH1* | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 5000000 | 5000000 |  |  | 1.1 | 1.1
2017-04-28 | April 2017 Review | New approval | Regional Improvements | Road improvements | Northland Highway & Network Operations | SH10 Kaeo Bridge upgrade | Implementation | Construction | HM_ | HML* | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 15700000 | 15700000 |  | 0.6 | 0.6 | 0.6
2017-04-28 | April 2017 Review | New approval | Regional Improvements | Road improvements | Northland Highway & Network Operations | SH10 Kaeo Bridge upgrade | Pre-implementation* |  | HM_ | HML* | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1000000 | 1000000 |  | 0.6 | 0.6 | 0.6
2017-04-26 | April 2017 Review | New approval | Regional Improvements | Road improvements | Tasman Highway & Network Operations | Kaikoura Nov 2016 EQ: Lewis Pass Altern Upg Rout - Tasman | Implementation | Implementation | HM1.4 | HM1-2.9 | Y | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 14979600 | 14979600 |  | 1.4 | 1.4 | 1.4
2017-04-19 | April 2017 Review | New approval | Regional Improvements | Road improvements | Waikato Highway & Network Operations | SH3 (Hamilton to Ohaupo) Improvements, NSRRP | Detailed Business Case | Single stage business case | HH66 | HH1-2.9 | Y | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 489799 | 489799 |  | 66 | 2 | 2
2017-04-12 | April 2017 Review | New Approval Programmes | Road safety promotion | Promotion, education and advertising | Northland Highway & Network Operations | 2016/18 RSP Auckland Northland HNO | Implementation |  | HH1-2.9 | HH1-2.9 | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 102600 | 102600
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Cycle path maintenance | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -2533 | -1342
2017-04-03 | April 2017 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Upper Hutt City Council | Railway Walking and Cycling Path | Design | Railway Walking and Cycling Path | HH4.8 | MH4.8 | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 4.8 | 4.8 | 4.8
2017-04-03 | April 2017 Review | Cash flow adjustment | External funding | Cycling facilities | Upper Hutt City Council | UCF Funding Administration | Implementation |  | HH4.7 | HH4.7 | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 4.7 | 4.7 | 4.7
2017-04-10 | April 2017 Review | Cash flow adjustment | External funding | Cycling facilities | Whangarei District Council | Cycleways Construction 2015/18 | Construction | UCP Cycleway Construction (UCF) | MH0 | MHH | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 0 | 5.7
2017-04-10 | April 2017 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Whangarei District Council | Cycleways Construction 2015/18 | Construction | UCP Cycleway Construction (NLTF) | MH0 | MHH | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 0 | 5.7
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Drainage renewals | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1423560 | 754486
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Environmental maintenance | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 275534 | 146034
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Level crossing warning devices | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -500 | -265
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road improvements | Minor improvements | Whangarei District Council | Minor improvements 2015-18 | Local Roads |  | HMH |  | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Network and asset management | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 68470 | 36289
2017-04-27 | April 2017 Review | Cash flow adjustment | State highway improvements | New roads | Auckland Highway & Network Operations | SH1 Puhoi to Warkworth RoNS Detailed Design and Construction | Pre-implementation* | Procurement & Design | HM1.1 | HML | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 1.1 | 1.1
2017-04-20 | April 2017 Review | Cash flow adjustment | State highway improvements | New roads | Canterbury Highway & Network Operations | Broughs Road Extension | Construction | Construction | HHM | HH3.6 | Y | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 3.6 | 0 | 3.6
2017-04-13 | April 2017 Review | Cash flow adjustment | Local road improvements | New roads | Queenstown-Lakes District Council | Eastern Access Road | Construction |  | HH13.9 | HHL | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 13.9 | 13.9
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Operational traffic management | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 180126 | 95466
2017-04-18 | April 2017 Review | Cash flow adjustment | Local road improvements | Resilience improvements | Hutt City Council | Bridge Corrosion Protection | Construction |  | HHM | HHM | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2017-04-20 | April 2017 Review | Cash flow adjustment | State highway improvements | Road improvements | BOP Highway & Network Operations | SH2: Baypark to Bayfair Link Upgrade (was MGI) | Construction | Implementation | HH2.5 | HHM | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 2.5 | 2.5
2017-04-12 | April 2017 Review | Cash flow adjustment | State highway improvements | Road improvements | Northland Highway & Network Operations | SH1 - Whangarei to Port Marsden Highway | Detailed Business Case | Single stage IBC/DBC | HH1.1 | HH1.1 | N | 3 | Approved with conditions | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Investment Transport online or by request | 0 | 0 | subject to, as conditions subsequent, hold points after the development of a short-list of options for each section to provide assurance to the VAC that the short-lists have been developed following an appropriately robust process. |  | 1.1 | 1.1
2017-04-20 | April 2017 Review | Cash flow adjustment | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH1 Wex Long Swamp Section | Construction | implementation of Construction | HH1.3 | HHL | Y | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 1.3 | 1.3
2017-04-26 | April 2017 Review | Cash flow adjustment | Regional Improvements | Road improvements | Waikato Highway & Network Operations | SH25 Coromandel Motorcycle Demonstration Project - stage 2 | Construction | Construction | HH7.3 | HHM | Y | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 7.3 | 7.2 | 7.2
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Routine drainage maintenance | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 269126 | 142636
2017-04-24 | April 2017 Review | Cash flow adjustment | Local road improvements | Seal extension | Rangitikei District Council | Taihape Napier Road Seal Extension (R) | Construction |  | LMH | LMH | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 3.2 | 3.2
2017-04-18 | April 2017 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH |  | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 360123 | 190865
2017-04-18 | April 2017 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Hutt City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH |  | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1549223 | 790104
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -5425194 | -2875353
2017-04-18 | April 2017 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Hutt City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH |  | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1549222 | -790102
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 975666 | 517103
2017-04-18 | April 2017 Review | Cash flow adjustment | Local road maintenance | Structures component replacements | Hutt City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH |  | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Structures component replacements | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1235000 | 654550
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Structures maintenance | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -7000 | -3710
2017-04-18 | April 2017 Review | Cash flow adjustment | Local road maintenance | Traffic services maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH |  | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1 | -1
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Traffic services maintenance | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 157808 | 83639
2017-04-18 | April 2017 Review | Cash flow adjustment | Local road maintenance | Traffic services renewals | Hutt City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH |  | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Traffic services renewals | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 518334 | 274718
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Unsealed pavement maintenance | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -65666 | -34803
2017-04-10 | April 2017 Review | Cash flow adjustment | Local road maintenance | Unsealed road metalling | Whangarei District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 37146 | 19687
2017-04-20 | April 2017 Review | Cash flow adjustment | Walking and cycling improvements | Walking facilities | Waikato Highway & Network Operations | SH1 Cobham Drive Pedestrian Facility | Construction | Cobham Drive Pedestrian Facility | HH2.6 | HH2.6 | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 2.6 | 2.6 | 2.6
2017-04-18 | April 2017 Review | Cost / Scope adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Waterview Connection Cycleway / Shared Path | Design | Waterview Connection Cycleway/Shared Path - DES | HH1.2 | HH2.0 | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 638065 | 325413 |  | 1.2 | 2 | 1.1
2017-04-11 | April 2017 Review | Cost / Scope adjustment | Walking and cycling improvements | Cycling facilities | Christchurch City Council | Major Cycleway: Papanui Parallel (Section 1, 2, 3 and 4) UCF | Detailed Business Case | Detailed BC- NZTA/Local Share Funding | HM3.2 | HH3.2 | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -72784 | -35664 |  | 3.2 | 3.2 | 3.2
2017-04-11 | April 2017 Review | Cost / Scope adjustment | Walking and cycling improvements | Cycling facilities | Christchurch City Council | Major Cycleway: Uni-Cycle (University to City) UCF | Construction | Hagley Park to Riccarton Bush Section 2 NZTA/Local | HH5.9 | HH5.9 | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 4564 |  | 5.9 | 5.9 | 5.9
2017-04-18 | April 2017 Review | Cost / Scope adjustment | External funding | Cycling facilities | Hutt City Council | The Beltway Investigation Design Delivery | Implementation | UCF ADMIN (BELTWAY) | HH6.5 | HM*6.5 | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | -840097 |  | 6.5 | 6.5 | 6.5
2017-04-10 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Drainage renewals | Mackenzie District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH |  | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 80000 | 42000
2017-04-11 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Christchurch City Council | EW - Ferrymead Bridge - EQ Reinstatement - NLTP Funding | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -428544 | -380183
2017-04-07 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Hurunui District Council | Kaikoura Earthquake 14 November 2016 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | -2259114
2017-04-07 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Hurunui District Council | Kaikoura Earthquake 14 November 2016 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 129665
2017-04-07 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Hurunui District Council | Kaikoura Earthquake 14 November 2016 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 206250
2017-04-07 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Hurunui District Council | Kaikoura Earthquake 14 November 2016 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 2247523
2017-04-07 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Hurunui District Council | Kaikoura Earthquake 14 November 2016 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | -172250
2017-04-07 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Hurunui District Council | Kaikoura Earthquake 14 November 2016 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 889954
2017-04-07 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Hurunui District Council | Kaikoura Earthquake 14 November 2016 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | -206250
2017-04-07 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Hurunui District Council | Kaikoura Earthquake 14 November 2016 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | -2377188
2017-04-07 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Hurunui District Council | Kaikoura Earthquake 14 November 2016 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 1369160
2017-04-07 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Hurunui District Council | Kaikoura Earthquake 14 November 2016 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 172250
2017-04-11 | April 2017 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Nelson Highway & Network Operations | Emergency Works Nelson December Storm Events 11/12 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -524570 | -524570
2017-04-27 | April 2017 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | West Coast Highway & Network Operations | (E) May 14 West Coast | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -10251 | -10251
2017-04-10 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Whangarei District Council | E/W 2014/15: Various Sites | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -200000 | -106000
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Auckland Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 180576 | 180576
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | BOP Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHM |  | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -223155 | -223155
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | BOP Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHM |  | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 44118 | 44118
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Gisborne Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | MMM |  | N | 6 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 153900 | 153900
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Hawkes Bay Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | MMM |  | N | 6 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 30780 | 30780
2017-04-04 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Hawkes Bay Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | MMM |  | N | 6 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 35910 | 35910
2017-04-13 | April 2017 Review | Cost / Scope adjustment | Local road improvements | Minor improvements | Mackenzie District Council | Minor improvements 2015-18 | Local Roads |  | HMH |  | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 50000 | 26500
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Manawatu/Wanganui Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | MMM |  | N | 6 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -15390 | -15390
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Nelson Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 89262 | 89262
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Northland Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 52326 | 52326
2017-04-28 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Northland Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -66690 | -66690
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Otago Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HMH |  | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 89262 | 89262
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Southland Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HMH |  | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 25650 | 25650
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Taranaki Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | MMM |  | N | 6 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 61560 | 61560
2017-04-28 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Tasman Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 66690 | 66690
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Tasman Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 123120 | 123120
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Tasman Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 223155 | 223155
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Tasman Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -920322 | -920322
2017-04-04 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Tasman Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 17595 | 17595
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Waikato Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHM |  | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -87210 | -87210
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Waikato Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHM |  | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 192888 | 192888
2017-04-06 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | West Coast Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | MHH |  | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -20520 | -20520
2017-04-20 | April 2017 Review | Cost / Scope adjustment | State highway improvements | New roads | Auckland Highway & Network Operations | East West Link -part of Auckland Accelerated Programme(AAP) | Detailed Business Case | Detailed Business Case | HH1.9 | HHL | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -2465 | -2465 |  |  | 1.9 | 1.9
2017-04-20 | April 2017 Review | Cost / Scope adjustment | State highway improvements | New roads | BOP Highway & Network Operations | Hairini Link - Stage 4 | Design | Hairini | HM2.1 | HMM | Y | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -2583489 | -2583489 |  |  | 2.1 | 2.5
2017-04-20 | April 2017 Review | Cost / Scope adjustment | State highway improvements | New roads | Canterbury Highway & Network Operations | Broughs Road Extension | Design | Design | HHM | HH3.6 | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -25651 | -25651 |  | 3.6 | 0 | 3.6
2017-04-20 | April 2017 Review | Cost / Scope adjustment | State highway improvements | New roads | Canterbury Highway & Network Operations | CHCH Southern Motorway HJR to Rolleston (Stage 2 & 3) | Design |  | HH2.4 | HHM | Y | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -730591 | -730591 |  |  | 2.4 | 1.5
2017-04-20 | April 2017 Review | Cost / Scope adjustment | State highway improvements | New roads | Canterbury Highway & Network Operations | Groynes to Sawyers Arms 4L | Construction | Groynes To Sawyers Arms 4L | HMM | HHM | Y | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -2841017 | -2841017 |  |  | 1.4 | 1.4
2017-04-11 | April 2017 Review | Cost / Scope adjustment | Local road improvements | New roads | Christchurch City Council | Wigram Magdala Link | Construction | Wigram Magdala Grade Separated Link | HM4 | HMH | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -305008 | -164705 |  | 4 | 4.7 | 4.7
2017-04-13 | April 2017 Review | Cost / Scope adjustment | Local road improvements | New roads | Queenstown-Lakes District Council | Frankton Flats Road 2 | Construction | Frankton Flats Road 2 | HMH | HHH | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -2549947 | -1427970 |  |  | 4.5 | 3.8
2017-04-20 | April 2017 Review | Cost / Scope adjustment | State highway improvements | New traffic management facilities | Canterbury Highway & Network Operations | Barters/Main Sth intersection | Construction | Construction | HH.6 | HHM | Y | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1364427 | -1364427 |  |  | 0.6 | 0.6
2017-04-20 | April 2017 Review | Cost / Scope adjustment | State highway improvements | New traffic management facilities | Canterbury Highway & Network Operations | SH73 Curletts Road Improvements | Construction |  | HMH | HMH | Y | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -35751 | -35751 |  |  | 5 | 5
2017-04-11 | April 2017 Review | Cost / Scope adjustment | Local road improvements | New traffic management facilities | Christchurch City Council | AAC TP30k: Slow Core | Construction |  | HH2.2 | HH22.8 | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | -796 |  | 2.2 | 22.8 | 22.8
2017-04-18 | April 2017 Review | Cost / Scope adjustment | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Safer Journeys Signature Programme | Programme business case |  | MML* | MML* | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 639 | 639
2017-04-10 | April 2017 Review | Cost / Scope adjustment | Road safety promotion | Promotion, education and advertising | Whangarei District Council | Road Safety Promotion 2015-18 | Implementation |  | HH5+ | HHH | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -79592 | -42184
2017-04-10 | April 2017 Review | Cost / Scope adjustment | Road safety promotion | Promotion, education and advertising | Whangarei District Council | Road Safety Promotion 2015-18 | Implementation |  | MM5+ | MHH | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -20000 | -10600
2017-04-21 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Property purchase (State highways) | Auckland Highway & Network Operations | SH22 Crown Road Improvements | Property |  | HHM | HMM | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 15142 | 15142 |  |  | 3.4 | 3.4
2017-04-06 | April 2017 Review | Cost / Scope adjustment | External funding | Property purchase (State highways) | Canterbury Highway & Network Operations | Kaikoura Nov 2016 EQ: SH1 between Clarence & Oaro (Crown | Property | Property | ___ | HH1.5 | Y | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1026000 | -1026000 |  |  | 1.5 | 1.5
2017-04-26 | April 2017 Review | Cost / Scope adjustment | Public transport | Public transport information supply, operations and maintenance | NZ Transport Agency | Mobility as a Service â€“ Pilot (Queenstown/Auckland Airport | Detailed Business Case | DBC/Pilot | HM0 | HM0.0 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -3100000 | -3100000 |  |  | 0 | 0
2017-04-21 | April 2017 Review | Cost / Scope adjustment | External funding | Replacement of bridges and other structures | Marlborough Highway & Network Operations | Opawa Bridge Replacement | Detailed Business Case | Investigation | MM*L* | MLL* | N | 7 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 51223 | 51223 |  |  | 0 | 0
2017-04-21 | April 2017 Review | Cost / Scope adjustment | Regional Improvements | Replacement of bridges and other structures | West Coast Highway & Network Operations | Taramakau Road Bridge | Design | Design | HM1.9 | HH1.9 | Y | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 55967 | 55967 |  |  | 1.9 | 1.9
2017-04-28 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Canterbury Highway & Network Operations | Christchurch Bus Priority Measures (State Highway Component) | Construction |  | HMM | MMM | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -107310 | -107310 |  |  | 5.8
2017-04-20 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Canterbury Highway & Network Operations | Okarahia to Conway Side Protection | Construction | Construction | HMM | HMM | Y | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -116175 | -116175 |  |  | 0 | 2.4
2017-04-11 | April 2017 Review | Cost / Scope adjustment | Local road improvements | Road improvements | Christchurch City Council | AAC Two-way conversion: Kilmore & Salisbury | Detailed Business Case |  | HM5.5 | HHH | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -413000 | -202370 |  | 5.5 | 5.5 | 5.5
2017-04-11 | April 2017 Review | Cost / Scope adjustment | Local road improvements | Road improvements | Christchurch City Council | Intersection Safety: Gasson/ Madras/ Moorhouse (1) | Construction | Design and construction | HM4 | HM5.1 | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 7719 |  | 4 | 0 | 5.1
2017-04-11 | April 2017 Review | Cost / Scope adjustment | Local road improvements | Road improvements | Christchurch City Council | Main North Road Corridor Optimisation | Construction | Bus lane construction and intersection improvement | HM2.8 | HH2.8 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -180883 | -88632 |  | 2.8 | 0 | 2.8
2017-04-04 | April 2017 Review | Cost / Scope adjustment | Local road improvements | Road improvements | Dunedin City Council | Central City Safety and Accessibility Upgrade | Indicative Business Case |  | HM2.4 | HH2.4 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 75000 | 43500 |  |  | 2.4 | 2.4
2017-04-12 | April 2017 Review | Cost / Scope adjustment | Local road improvements | Road improvements | Far North District Council | LED Streetlight upgrades 2015 - 2018 | Construction | LED streetlight upgrades 2015 - 2018 | MH99 | HMH | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 196000 |  | 99 | 99 | 99
2017-04-20 | April 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Hawkes Bay Highway & Network Operations | SH2 Pakipaki to Waipukurau | Implementation | Implementation | HH1.7 | HH1.7 | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -651738 | -651738 |  | 1.7 | 1.7 | 1.7
2017-04-20 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Manawatu/Wanganui Highway & Network Operations | SH1 Manakau Village Safety Improvements | Implementation | Construction | HH0 | HHL | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -532119 | -532119 |  |  | 0 | 2
2017-04-26 | April 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Marlborough Highway & Network Operations | SH1 SH62 Spring Creek Intersection RAB | Construction |  | MM*2 | HM2.0 | N | 7 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 718200 | 718200 |  |  | 2 | 2
2017-04-20 | April 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Nelson Highway & Network Operations | SH6 Quarantine Road I/S | Construction | Construction | MM12.1 | MMH | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -427511 | -427511 |  |  | 12.1 | 12.1
2017-04-20 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Northland Highway & Network Operations | 09-12 Roading - Mountain Road Passing Lane SB Extn | Construction | Mountain Road Passing Lane SB Extn | MMM | MMM | N | 6 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -666927 | -666927 |  | 0 | 0 | 0
2017-04-21 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Otago Highway & Network Operations | HPMV - SH8 - Queenstown to Dunedin | Implementation | Construction | HMH | HMH | Y | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 109834 | 109834 |  |  | 4.4 | 4.4
2017-04-20 | April 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Waikato Highway & Network Operations | Mangatawhiri Deviation | Construction |  | MMM |  | Y | 6 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -22469 | -22469
2017-04-10 | April 2017 Review | Cost / Scope adjustment | Local road improvements | Road improvements | Whangarei District Council | Mill Road/Nixon Street Upgrades | Construction | Mill/Nixon Upgrades | MMH | MMH | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 360000 | 219600 |  |  | 8.2 | 8.2
2017-04-20 | April 2017 Review | Cost / Scope adjustment | Local road improvements | Seal extension | Rangitikei District Council | Taihape Napier Road Seal Extension (R) | Construction |  | LMH | LMH | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | -36277 |  |  | 3.2 | 3.2
2017-04-05 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Sealed pavement maintenance | Ruapehu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH |  | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | -1000
2017-04-10 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Sealed road pavement rehabilitation | Porirua City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH |  | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 300000 | 149000
2017-04-10 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Sealed road resurfacing | Mackenzie District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH |  | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 294000 | 154530
2017-04-10 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Sealed road resurfacing | Porirua City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH |  | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1200000 | 596000
2017-04-05 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Sealed road resurfacing | Ruapehu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH |  | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | -700
2017-04-10 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Structures component replacements | Mackenzie District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH |  | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 50000 | 26500
2017-04-10 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Unsealed road metalling | Mackenzie District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH |  | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 100000 | 52500
2017-04-05 | April 2017 Review | Cost / Scope adjustment | Local road maintenance | Unsealed road metalling | Ruapehu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH |  | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | -900
2017-04-20 | April 2017 Review | Cost / Scope adjustment | Walking and cycling improvements | Walking facilities | Waikato Highway & Network Operations | SH1 Cobham Drive Pedestrian Facility | Design | Design phase (Pre-implementation) | HH2.6 | HH2.6 | Y | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1500 | -1500 |  | 2.6 | 2.6 | 2.6