## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2022-05-09 | May 2022 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Northland Regional Council | Activity Management Planning | Implementation | Regional Public Transport & Road Safety Planning | HHL | HHVH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This is a standard funding application at the start of an NLTP period. The respective AMPs contribute to the priority outcomes of the relevant GPS. See CFO approval docs for more details. | 845321 | 456472 |  |  | 1 | 1 |  | 277132 |  | 115647
2022-05-09 | May 2022 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Waimakariri District Council | Activity Management Plan 2021-24 | Improvement to existing AMP |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The AMP is a key document in the planning and maintenance of the District's network. Regional staff have worked and continue to work with council staff to identify any further areas that need improvement. Terms of reference has been reviewed and is attached in TIO. | 350000 | 178500 | [5 empty] | 280939 |  | 116923
2022-05-09 | May 2022 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Wellington City Council | Activity Management Plan 2021-24 | Improvement to existing AMP |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This is a standard funding application at the start of an NLTP period. The respective AMPs contribute to the priority outcomes of the relevant GPS. See CFO approval docs for more details. | 298500 | 152235 | [5 empty] | 277492 |  | 116924
2022-05-02 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Auckland Transport | Meadowbank - Kohimarama Connectivity Project | Implementation | MKCP - Northern Connection | HML | HHL | N | 6 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits of this project are: Providing better travel options through its positive impact on access to opportunities as it creates improved walking and cycling links to primary and secondary education, public transport and complements Auckland's cycleway network; and Increasing the number of pedestrians and cyclists through the construction of a shared path that is safe and convenient; and Improving the perceived and actual safety risks for pedestrians and cyclists through the construction of a safer separated cycle route; and Increasing the useability of the Auckland Cycle Network which will improve access and provide greater transport choice. | 2203448 | 1123758 |  |  | 0 | 1.1 | 452.2646 | 264614 |  | 116272
2022-05-02 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Auckland Transport | Meadowbank - Kohimarama Connectivity Project | Pre-implementation* | MKCP - Northern & Southern Connection | HML | HHL | N | 6 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits of this project are: Providing better travel options through its positive impact on access to opportunities as it creates improved walking and cycling links to primary and secondary education, public transport and complements Aucklands cycleway network; and Increasing the number of pedestrians and cyclists through the construction of a shared path that is safe and convenient; and Improving the perceived and actual safety risks for pedestrians and cyclists through the construction of a safer separated cycle route; and Increasing the useability of the Auckland Cycle Network which will improve access and provide greater transport choice. | 2905600 | 1481856 |  |  | 0 | 1.1 | 452.2775 | 277495 |  | 116273
2022-05-11 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Auckland Transport | SfP - Funding the Foundations | Pre-implementation* | SfP - Funding Foundations (Pre-Imp) | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Auckland Transport has been confirmed by Multimodal & Innovation team | 186312 | 167681 |  |  |  | 1 | 452.2813 | 281322 |  | 117344
2022-05-11 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Central Hawkes Bay District Council | SFP - CHBDC Streets for people | Pre-implementation* | SfP - Main Street Waipawa | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to CHBDC has been confirmed by Multimodal & Innovation team | 97790 | 88011 | [5 empty] | 281361 |  | 117483
2022-05-12 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Christchurch City Council | CCP Lichfield Street (Madras to Manchester) (SfP) | Pre-implementation* | SFP Development of Application | HMM | HHM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Christchurch CC has been confirmed by Multimodal & Innovation team | 178200 | 160380 |  |  |  | 4.1 |  | 281399 |  | 117526
2022-05-11 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Gisborne District Council | SfP Gisborne Community Trials | Pre-implementation* | SfP Gisborne Community Trials | VHHL | HHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Gisborne DC has been confirmed by Multimodal & Innovation team | 66550 | 59895 |  |  | 1 | 1 |  | 281362 |  | 117446
2022-05-11 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Hutt City Council | SfP Hutt City Suburban Centres Tactical Urbanism | Pre-implementation* | SfP Suburban Centre TU Pre-Imp | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Hutt City Council has been confirmed by Multimodal & Innovation team | 94512 | 85061 | [5 empty] | 281383 |  | 117484
2022-05-11 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Napier City Council | SfP Walking and Cycling | Pre-implementation* | SFP-Walking and Cycling Pre-implementation | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Napier City Council has been confirmed by Multimodal & Innovation team | 60100 | 54090 |  |  | 1 | 1 |  | 281358 |  | 117443
2022-05-17 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Nelson City Council | SfP Hospital Connection | Implementation | SfP Hospital Connection | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Nelson CC has been confirmed by Multimodal & Innovation team | 157700 | 141930 |  |  | 1 | 1 |  | 281441 |  | 117576
2022-05-25 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Palmerston North City Council | SfP | Pre-implementation* | SfP - Featherston Street | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Palmerston North CC has been confirmed by Multimodal & Innovation team | 136158 | 122542 |  |  |  | 1 |  | 281559 |  | 117752
2022-05-11 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Tasman District Council | SfP Tasman Towns | Pre-implementation* | SfP Tasman Towns | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Tasman DC has been confirmed by Multimodal & Innovation team | 70422 | 63380 |  |  |  | 1 |  | 281364 |  | 117449
2022-05-11 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Taupo District Council | SfP - Safer connections to Taupo Schools | Pre-implementation* | SfP - Safer connections to Schools in Taupo | HHL | HHH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Taupo DC has been confirmed by Multimodal & Innovation team | 85212 | 76691 |  |  |  | 1 |  | 281378 |  | 117473
2022-05-11 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Tauranga City Council | SfP - Streets for People - Tauranga City | Pre-implementation* | SfP - Streets for People - Te Papa/Arataki | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Tauranga CC has been confirmed by Multimodal & Innovation team | 127600 | 114840 |  |  | 1 | 10 | Pre-implementation | 281381 |  | 117475
2022-05-17 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Timaru District Council | SfP Timaru District Council 2021-24 | Pre-implementation* | SfP - Timaru | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Timaru DC has been confirmed by Multimodal & Innovation team | 143300 | 128970 |  |  |  | 1 |  | 281446 |  | 117575
2022-05-12 | May 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Wellington City Council | Transitional Cycleways Programme (ex Accelerated)(SfP) | Pre-implementation* | SfP Wellington Transitional Programme | HHL | VHHM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Wellington CC has been confirmed by Multimodal & Innovation team | 130579 | 117521 |  |  |  | 3.5 | SfP Wellington Transitional Programme | 281363 |  | 117448
2022-05-16 | May 2022 Review | New approval | Local road maintenance | Emergency works | Carterton District Council | Emergency Works February 2022 Flooding Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | That the Regional Manager Wellington/Top of South, Transport Services: Approves $348,811 ($182,882 NLTF) at a transitional FAR 52.43% for recovery from the February 2022 district wide heavy rainfall event. | 348811 | 182882 |  |  |  |  | Initial response and repair | 280798 |  | 117009
2022-05-27 | May 2022 Review | New approval | Local road maintenance | Emergency works | Far North District Council | EW March 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | refer report in Supporting docs. | 213000 | 146970 |  |  |  |  | EW March 2022 | 281400 |  | 117528
2022-05-24 | May 2022 Review | New approval | Local road maintenance | Emergency works | Horowhenua District Council | June 2021 Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | As per regional recommendation | 659050 | 408611 | [5 empty] | 281158 |  | 117223
2022-05-27 | May 2022 Review | New approval | Local road maintenance | Emergency works | Kaipara District Council | EW - Ex Tropical Cyclone Fili March 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | refer report in supporting docs. | 192000 | 119040 |  |  |  |  | Immediate response and permanent repair | 281380 |  | 117644
2022-05-16 | May 2022 Review | New approval | Local road maintenance | Emergency works | Kapiti Coast District Council | EW December Storm 2021 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | Recommends that the Manager Systems Manager (Transport Services) approves $500,000 for EW Storm Event 2021 at a FAR of 51% (NLTF $255,000). | 500000 | 255000 |  |  |  |  | 1794G category 141 | 280803 |  | 116753
2022-05-12 | May 2022 Review | New approval | Local road maintenance | Emergency works | Manawatu District Council | Emergency Works December 2021 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Recommended as per regional office. | 1096123 | 580945 |  |  |  |  | Emergency Works December 2021 | 280615 |  | 116425
2022-05-18 | May 2022 Review | New approval | Local road maintenance | Emergency works | Marlborough District Council | Emergency Works -July 21 Storm Event - Response | Construction |  | ___ |  | N |  | Approved | Approved by NZTA Board/Board Committee | approving $63.6M (P50). Further requests are expected and Board delegated CEO to release funding over $63.6M if required. | 63600000 | 60420000 |  |  |  |  | Recovery | 279315 |  | 116267
2022-05-04 | May 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (BOP) | EW 35 Opo-C Run/2 Opo-Gisb HR 20211114 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Happy to support this application. Emergency works funding to be used to recover the network to the same level of service that it was at date this storm occurred. | 1404000 | 1404000 | [5 empty] | 280475 | 60066436 | 117268
2022-05-05 | May 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (Waikato) | EW East Waikato RE Cyclone Dovi 20220212 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Acknowledging that option analysis i still in progress as design reports have only just been received. | 2350680 | 2350680 | [5 empty] | 280739 | 60066754 | 117463
2022-05-02 | May 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (West Coast) | EW West Coast HR 20220202 | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Transport Services) | Enable restoration of damage caused by the heavy rain event to restore level of service. | 5522383 | 5522383 | [5 empty] | 280681 | 60066671 | 117247
2022-05-30 | May 2022 Review | New approval | Local road maintenance | Emergency works | South Wairarapa District Council | Emergency Works Cape Palliser Rd Swell damage April 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | Recommends that the Manager Systems Manager (Transport Services) approves $855,572 for Emergency Works Cape Palliser Rd Swell damage April 2022 at a FAR of 100% (NLTF $855,572). | 855572 | 855572 |  |  |  |  | initial response and reinstate rock revetments | 281384 |  | 117527
2022-05-27 | May 2022 Review | New approval | Local road maintenance | Emergency works | South Wairarapa District Council | Emergency Works February Flooding Event 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | Recommends that the Manager Systems Manager (Transport Services) approves $322,179 for EW February Flooding Event 2022 at a FAR of 52.47% (NLTF $169,033). | 322179 | 169033 |  |  |  |  | Initial response and repair | 280800 |  | 117008
2022-05-25 | May 2022 Review | New approval | Local road maintenance | Emergency works | Tasman District Council | EW Storm Event July 2021 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | That the Senior Manager System Management: APPROVES $4,567,000 (total NLTF share $2,910,178) emergency works funding for Tasman District Council for the July 2021 Storm Event. NOTES $1,661,962 will be at 51% (NLTF $847,601) and $2,905,038 will be funded at 71% (NLTF 2,062,577). | 1661962 | 847601 | [5 empty] | 279855 |  | 115185
2022-05-16 | May 2022 Review | New approval | Local road maintenance | Emergency works | Waimakariri District Council | E/W February 2022 Flood Event Waimakariri District | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Recommendation That the Regional Manager - Maintenance and Operations: Approves Waimakariri District Councilâ€™s Emergency Works request at a total cost of $737,000. The net NLTF Share for this event is broken down into $239,270 for Financial Year 21/22 and $204,000 for Financial Year 22/23 (NLTF total Share $443,270). | 737000 | 443270 | [5 empty] | 281030 |  | 117572
2022-05-30 | May 2022 Review | New approval | Local road improvements | New activities influencing users of the transport system | Dunedin City Council | SFDT - Central City Parking Management plan | Single-Stage Business Case | Parking plan SSBC | VHHL | MHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | â€¢ Very high alignment to GPS and this project is identified as a key activity to progress in the Shaping Future Dunedin Transport PBC; â€¢ Satisfies Land Transport Management Act 2003 requirements; and â€¢ Funding prioritisation and availability has been confirmed. | 150000 | 78400 |  |  | 2.3 |  | Central City Parking Wayfinding, data aggregation and technology systems | 277501 |  | 116757
2022-05-11 | May 2022 Review | New approval | Public transport services | New activities influencing users of the transport system | NZ Transport Agency | National Mode Shift Campaign | Single-Stage Business Case | SSBC National Mode Shift Campaign - wc421 | MHVH | VHHM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | New phase created to fix incorrect wc (wc524 to 421) Cost neutral interphase change. | 97200 | 97200 |  |  | 5 |  | 60067381 SAP ID | 281438 |  | 117563
2022-05-16 | May 2022 Review | New approval | Public transport services | New activities influencing users of the transport system | Queenstown-Lakes District Council | Travel Demand Management | Single-Stage Business Case | SSBC | VHHM | VHHVH | N | 1 | Approved | Approved by Chief Financial Officer (CFO) | The TDM Business Case will identify a prioritised work programme to focus investment and effort in delivering the most effective and appropriate initiatives to achieve strategic objectives and complement infrastructure investment already underway or planned. This activity aligns to the GPS outcome area of better travel options. Funding allows for a Single Stage Business Case to determine a suite of travel demand management initiatives across Queenstown. LTMA Requirements have been met and funding prioritised. | 80000 | 40800 |  |  | 2.3 | 2.3 |  | 277212 |  | 117362
2022-05-16 | May 2022 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Auckland Transport | Wellesley Street Bus Improvements | Pre-implementation* | Stage 1 - Central Blocks - Pre-Imp | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The pre-implementation phase for Stage 1 of the WSBI project is being requested ahead of DBC completion to enable eventual delivery of Stage 1 (between Queen and Albert streets) ahead of CRL Aotea Station opening in late 2024. The reasons for this are explained in the funding memo attached in Supporting Documents. WSBI will provide bus priority on this key east-west PT corridor plus greatly enhanced facilities for pedestrians and cyclists and is an appropriate response to issues identified along the corridor. | 2114000 | 1078140 |  |  | 0 | 1.6 | 561.2382 | 238154 |  | 117129
2022-05-09 | May 2022 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Auckland Transport | WhangaparÄoa Bus Access | Detailed Business Case | Whangaparaoa PT Station DBC | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | It is imperative the business case commences as soon as practicable given the interface with Penlink and the ability to influence the design as soon as possible to avoid additional re-design and cost. | 932703 | 475679 |  |  |  | 1.1 | 561.2777 | 277674 |  | 117113
2022-05-12 | May 2022 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Tauranga City Council | CBD PT HUB (LONG-TERM) SSBC | Single-Stage Business Case | SSBC | VHHL | VHHH | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | High alignment to the GPS and builds on existing work that is programmed for Tauranga City Council. Large amount of previous work that sets the strategic direction and programme options, now required to confirm and develop preferred option for this activity. Scoping of this project has been thorough and in partnership clear pathway to next investment decision gate. Non delivery and progression of the project will have an impact on realising the estimated benefits of the total programme. | 600000 | 306000 |  |  | 2.7 | 2.7 | SSBC | 276654 |  | 117222
2022-05-09 | May 2022 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | Waikato Regional Council | Addendum to Te Huia SSBC-Interregional rail access post CRL | Single-Stage Business Case | Addendum to Te Huia SSC - PT Infrastructure | HHL | VHHVH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | High GPS alignment. | 300000 | 153000 |  |  | 0.5 | 0.5 | Addendum to Te Huia SSBC | 281398 |  | 117522
2022-05-12 | May 2022 Review | New approval | Public transport services | Passenger services - ferry | Far North District Council | Government reduced public transport fares scheme (Crown) | Implementation | Hokianga ferry service - Reduced fares | HHL | VHHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) |  | 8070 | 5568 | [5 empty] | 281226 |  | 117377
2022-05-19 | May 2022 Review | New approval | Public transport services | Passenger services - rail | Greater Wellington | Palmerston Nth-Wgtn Rail Passenger (Capital Connection) | Implementation | Additional Capital connect cost 100% NZTA | H_L | HHH | N | 0 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | Confirmed legal obligation | 1086479 | 1086479 | that this decision is reported to the May I&DC for noting as decision made by CFO under delegation |  | 9.4 | 9.4 | 100% Capital connect passthrough | 280355 |  | 115976
2022-05-10 | May 2022 Review | New approval | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Hawkes Bay) | SH5 Napier To Taupo | Programme business case |  | HML | HMM | N | 6 | Approved | Approved by Chief Financial Officer (CFO) | See PoE - value for money, GPS alignment | 400000 | 400000 | [5 empty] | 277810 | 60039010 | 117302
2022-05-25 | May 2022 Review | New approval | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Waikato) | Hamilton Southern Links Review 2021 | Programme business case |  | HML | MHL | N | 6 | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables Waka Kotahi to ensure the existing designation is well aligned to Hamilton City mode shift goals and wider climate change commitments | 349920 | 349920 | [5 empty] | 280918 | 60066055 | 116948
2022-05-11 | May 2022 Review | New approval | Investment management (incl. Transport Planning) | Regional land transport planning management | Horizons Manawatu | RLTP management MNWI | Implementation |  | V__ | V__ | N |  | Approved | Approved by Chief Financial Officer (CFO) | That the CFO approve funding for RLTP Management for the regions at a total cost of $14,539,604, NLTF contribution $7,595,052, and at the FAR rates as noted in Table 1 below from the Investment Management Activity Class Work Category Transport Planning WC001. Noting that this is approval at the individual regional level. | 455516 | 232312 |  |  |  |  | Implementation | 277996 |  | 115136
2022-05-11 | May 2022 Review | New approval | Investment management (incl. Transport Planning) | Regional land transport planning management | Taranaki Regional Council | Regional Land Transport Planning Management 2021-24 | Implementation |  | V__ | H__ | N |  | Approved | Approved by Chief Financial Officer (CFO) | A composite Point of Entry for RLTP Management for New Zealandâ€™s regions as per attached table approved by CFO | 312521 | 159386 |  |  |  |  | RLTP Taranaki | 277912 |  | 117464
2022-05-19 | May 2022 Review | New approval | Local road improvements | Resilience improvements | Auckland Transport | Kepa Road Slip Remediation Improvements | Single-Stage Business Case | SSBC - Kepa Road Slip Remediation Improvement | LLL | MML | Y | 9 | Approved | Approved by Auckland Transport Chief Financial Officer | This is approved under DFA - delegated funding arrangement with Auckland transport. AT can approve to a certain limit some projects and this is one of them. | 63000 | 32130 |  |  |  | 1 | 324.2776 | 277593 |  | 115997
2022-05-18 | May 2022 Review | New approval | Road to Zero | Road improvements | Auckland Transport | High Risk Intersections and Corridors | Implementation | HRIC Atkinson Ave SSC | HHM | VHHL | Y | 2 | Approved | Approved by Auckland Transport Chief Financial Officer |  | 5936068 | 3027394 |  |  |  | 4.5 | 324.2804 | 280417 |  | 117625
2022-05-18 | May 2022 Review | New approval | Road to Zero | Road improvements | Auckland Transport | High Risk Intersections and Corridors | Implementation | HRIC Ash St & Rata St SSC | HHM | VHHL | Y | 2 | Approved | Approved by Auckland Transport Chief Financial Officer |  | 4515127 | 2302714 |  |  |  | 4.5 | 324.2804 | 280416 |  | 117612
2022-05-05 | May 2022 Review | New approval | Road to Zero | Road improvements | Christchurch City Council | Greers, Northcote & Sawyers Arms Intersection Improvement | Pre-implementation* |  | HMM | HMM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Endorsed SSI | 290000 | 147900 |  |  |  | 4.4 |  | 281122 |  | 117182
2022-05-05 | May 2022 Review | New approval | Road to Zero | Road improvements | Christchurch City Council | Pound & Ryans Intersection Improvement | Pre-implementation* |  | VHMM | VHHM | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Endorsed SSI | 900000 | 459000 |  |  |  | 4.5 |  | 280677 |  | 116527
2022-05-10 | May 2022 Review | New approval | Local road improvements | Road improvements | Western BoP District Council | Omokoroa Transport Improvements | Single-Stage Business Case | SSBC | VHHL | VHHVH | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | See PoE high gps alignment | 1000000 | 510000 |  |  | 1 | 1 |  | 277197 |  | 117243
2022-05-03 | May 2022 Review | New approval | Local road improvements | Road improvements | Whangarei District Council | Port Rd/Kioreroa Rd Intersection Improvement | Implementation |  | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | There is a compelling case for investment as the intersection upgrade provides an opportunity to continue the shared path being constructed as part of the Port Road Limeburners Creek Bridge Widening works currently underway, thereby further providing safe access and crossing options for pedestrians and cyclists. | 6730000 | 3566900 |  |  |  | 2.6 |  | 276968 |  | 115749
2022-05-25 | May 2022 Review | New approval | Walking and cycling improvements | Walking facilities | Hastings District Council | SfP Streets for Schools | Pre-implementation* | SfP Streets for Schools Pre-Implementation | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Hastings DC has been confirmed by Multimodal & Innovation team | 128987 | 116088 |  |  |  | 4.5 |  | 281518 |  | 117643
2022-05-09 | May 2022 Review | New approval | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM ED Central City and SH1 walking cycling and safer speed | Implementation | CCPI | HHM | VHHH | N | 4 | Approved | Approved by Chief Financial Officer (CFO) |  | 3020243 | 1649948 |  |  | 1.2 | 1 |  | 279815 | 60053806 | 116786
2022-05-17 | May 2022 Review | New approval | Walking and cycling improvements | Walking facilities | Whanganui District Council | SFP - Streets for People - Whanganui District | Pre-implementation* | SfP Whanganui District | HHL | HHH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Whanganui DC has been confirmed by Multimodal & Innovation team | 94402 | 84962 |  |  |  | 1 | Streets for People Pre-implementation - Whanganui District | 281458 |  | 117603
2022-05-16 | May 2022 Review | Cash flow adjustment | Local road maintenance | Bridge and structures renewals | DOC (West Coast) | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | SPR |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Shifting wc 216 funding into wc 215. Original funding bid had mistakenly put funding for bridge components through wc216. Change does not affect overall funding allocation through West Coast programme. Disccussions with ACM Mark Weeds earlier this year and he accepted this reason for changing from 216 to 215. Cost neutral transaction, within MOR ALLOCATION. | -883949 | -450813 | [5 empty] | 275200 |  | 117442
2022-05-27 | May 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Airport Access - Short-term Improvements | Pre-implementation* | Airport Access - Mangere Cycling Improvement - PRE | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 1.3 | 1.3 | 452.2606 | 260577 |  | 117697
2022-05-27 | May 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Auckland Cycle Network - City Centre Network | Implementation | UCP - ACN CCN - Tamaki Drive (Seg 2-5) IMP (NLTF) | VHHH | HHH | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | -1 |  |  | 0 | 6.8 | 452.2415 | 241495 |  | 117688
2022-05-27 | May 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - Central Isthmus & Sandringham | Detailed Business Case | Cycling Investment - Central & Sandringham - DBC | HHM | HMM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 0 | 3.2 | 452.2613 | 261280 |  | 117700
2022-05-30 | May 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - City Centre & Fringe | Detailed Business Case | Cycling Investment - City Centre and Fringe - DBC | HHM | HMM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 0 | 3.2 | 452.2613 | 261263 |  | 117701
2022-05-27 | May 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - Mangere East | Single-Stage Business Case | Cycling Investment - Mangere East - SSBC | HHL | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 0 | 1.9 | 452.2613 | 261307 |  | 117704
2022-05-27 | May 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - Manukau | Single-Stage Business Case | Cycling Investment - Manukau - SSBC | HHL | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. This activity may come in under budget, AT will monitor and declare surplus as needed in early FY23. | 0 | 0 |  |  | 0 | 1.9 | 452.2613 | 261303 |  | 117690
2022-05-27 | May 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Meadowbank - Kohimarama Connectivity Project | Pre-implementation* | MKCP - Northern & Southern Connection | HML | HHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This activity is delayed and so completing a NLTF neutral cashflow to reflect current forecast. | 0 | 0 |  |  | 0 | 1.1 | 452.2775 | 277495 |  | 117703
2022-05-27 | May 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Urban Cycleways Programme - Links to Glen Innes | Implementation | Links to GI - IMP - Package 1 Taniwha Street | HHL | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 1.5 | 1.5 | 452.2801 | 280136 |  | 117689
2022-05-30 | May 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Christchurch City Council | Major Cycleway: Little River Link (Little River Route) UCF | Construction | Moorhouse to Barrington St Section 1 NZTA/Local | H_L | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This project is facing a delay, carrying forward approval to 2022/23 | 0 | 0 |  |  | 2.5 | 2.5 | 542/1991 | 244437 |  | 117748
2022-05-19 | May 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Wellington City Council | Wellington Cycle Network - Eastern Package | Implementation | Evans Bay - UCP Implementation - NLTF | VHHL | VHHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This reflects cashflow discussed with Paula from WCC | 0 | 0 |  |  | 0 | 2.5 |  | 249017 |  | 117554
2022-05-19 | May 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Wellington City Council | Wellington Cycle Network - Eastern Package | Implementation | Oriental Bay - UCP Implementation - NLTF | VHHL | VHHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Delays in finalizing designs plus constrains contractor resourcing due to covid | 0 | 0 |  |  | 0 | 2.5 |  | 263301 |  | 117556
2022-05-30 | May 2022 Review | Cash flow adjustment | Local road maintenance | Emergency works | Marlborough District Council | Emergency Works -July 21 Storm Event - Response | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | updated programme delivery | 0 | 0 |  |  |  |  | Recovery | 279315 |  | 117766
2022-05-06 | May 2022 Review | Cash flow adjustment | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | EW SH4 Nth of Raukawa Falls HR 20150619 | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Transport Services) | Move requested by Margarita B-G | 0 | 0 | [5 empty] | 270860 | 60058317 | 117486
2022-05-06 | May 2022 Review | Cash flow adjustment | State highway maintenance | Emergency works | NZTA (Tasman) | EW Region 10 SH60 Takaka Hill Feb 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Transport Services) | Correction of allocation to year of spend | 0 | 0 |  |  |  |  | 60049083 | 264335 | 60049083 | 117487
2022-05-11 | May 2022 Review | Cash flow adjustment | State highway maintenance | Emergency works | NZTA (West Coast) | EW West Coast Cyclone Fehi February 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Transport Services) | Covers spend as forecast | 0 | 0 |  |  |  |  | 60048960 | 264804 | 60048960 | 117570
2022-05-27 | May 2022 Review | Cash flow adjustment | Local road improvements | Low cost / low risk improvements | Auckland Transport | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  |  |  | 341.9003 | 275991 |  | 117652
2022-05-27 | May 2022 Review | Cash flow adjustment | Road to Zero | Low cost / low risk improvements | Auckland Transport | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  |  |  | 341.9023 | 275993 |  | 117683
2022-05-27 | May 2022 Review | Cash flow adjustment | Walking and cycling improvements | Low cost / low risk improvements | Auckland Transport | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | -1 |  |  |  |  | 341.9013 | 275990 |  | 117687
2022-05-13 | May 2022 Review | Cash flow adjustment | Local road improvements | Low cost / low risk improvements | Chatham Islands Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Timing changes to the Whangamoe Bridge replacement due to hold ups with consenting and landowner agreements have pushed the physical works into the 22/23 financial year. Some funding for the Owenga Wharf loading ramp to be brought forward to try and avoid similar consenting delays. | 0 | 0 | [5 empty] | 276022 |  | 117525
2022-05-27 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Low cost / low risk public transport improvements | Auckland Transport | Low cost / low risk improvements 2021-24 | Public transport infrastructure |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  |  |  | 531.9005 | 275989 |  | 117671
2022-05-30 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Low cost / low risk public transport improvements | Waikato District Council | Low cost / low risk improvements 2021-24 | Public transport infrastructure |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | project brought forward | 0 | -1 | [5 empty] | 276477 |  | 117584
2022-05-27 | May 2022 Review | Cash flow adjustment | Local road improvements | New roads | Auckland Transport | Matakana Link Road | Implementation | Matakana Link Road - IMP | HHH | MHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. This activity has had a partial surplus previously declared and is advancing to completion. It is expected that the activity will come in under budget and a further surplus will be declared as the activity is monitored (proposed in FY23). | 0 | 0 |  |  | 0 | 7.7 | 323.2489 | 248909 |  | 117654
2022-05-30 | May 2022 Review | Cash flow adjustment | Debt Funding | New roads | Auckland Transport | TNFG - North West HIF | Implementation | TNFG - NW HIF - Redhills (IMP) | HHH | H_H | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 programme monitor, this is a funding neutral cashflow to reflect the current forecast for the activity. | 0 | 0 |  |  | 5 | 1.4 | 323.264 | 263982 |  | 117722
2022-05-30 | May 2022 Review | Cash flow adjustment | Local road improvements | New roads | Auckland Transport | TNFG - North West HIF | Repayment | TNFG - Trig South HIF Repayment (NLTF) | HHH | H_H | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Due to changes made to the core IMP and Property Phases - this is realigning the repayment phase. | 0 | 0 |  |  | 5 | 1.4 | 324.2665 | 266463 |  | 117727
2022-05-30 | May 2022 Review | Cash flow adjustment | Local road improvements | New roads | Auckland Transport | TNFG - North West HIF | Repayment | TNFG - Redhills HIF Repayment (NLTF) | HHH | H_H | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Due to changes made to the core IMP and Property Phases - this is realigning the repayment phase. | 0 | 0 |  |  | 5 | 1.4 | 323.2665 | 266462 |  | 117724
2022-05-27 | May 2022 Review | Cash flow adjustment | Local road improvements | New roads | Auckland Transport | TNFG - South - Drury Local | Pre-implementation* | TNFG - South - Drury Local | VHHL | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. This project is also projecting a cost increase - this is still being discussed. | 0 | 0 |  |  | 1.1 | 1 | 324.2604 | 260420 |  | 117655
2022-05-27 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Auckland Transport | Northwest Bus Improvements | Pre-implementation* | Brigham Creek Station and P&R | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 1.7 | 1.7 | 561.2774 | 277423 |  | 117673
2022-05-27 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Auckland Transport | Northwest Bus Improvements | Property | Westgate Interchange (early deliverables) Prop | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. Aligning forecast to projected timing for construction commencement. | 0 | 0 |  |  | 1.7 | 1.7 | 561.2774 | 277420 |  | 117674
2022-05-27 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | Auckland Transport | AKL Level Crossing Removal Programme | Single-Stage Business Case | AKL Level Crossing Removal - Programme PBC/SSBC | MHL | HML | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  |  |  | 563.2792 | 279212 |  | 117665
2022-05-27 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | Auckland Transport | AKL Metro Train Capacity - Tranche 3 | Implementation | EMU Rolling Stock (Tranche 3) - IMP | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  |  | 2.1 | 563.2605 | 260527 |  | 117666
2022-05-27 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | Auckland Transport | AKL Metro Train Capacity - Tranche 3 | Pre-implementation* | EMU Stabling (Tranche 3) - Pre-imp | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  |  | 2.1 | 563.2776 | 277555 |  | 117667
2022-05-16 | May 2022 Review | Cash flow adjustment | Public transport services | Passenger services - bus | Otago Regional Council | Dunedin PT Improvements | Single-Stage Business Case | SSBC | VHML | VHML | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Delay in project due to late approval from various parties. Total cost unchanged. | 0 | 0 |  |  |  | 3.2 | SSBC | 277556 |  | 117542
2022-05-16 | May 2022 Review | Cash flow adjustment | Public transport services | Passenger services - bus | Otago Regional Council | Queenstown PT Improvements | Detailed Business Case | Queenstown PT DBC | VHHM | VHHM | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Delay in project due to late approval from various parties. Total cost unchanged. | 0 | 0 |  |  |  | 4.6 | Queenstown PT DBC | 277554 |  | 117543
2022-05-27 | May 2022 Review | Cash flow adjustment | Investment management (incl. Transport Planning) | Programme Business Case Development | Auckland Transport | Regional Public Transport Plan 2021-24 | Programme business case |  | HHM | HHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  |  |  | 4.277 | 276982 |  | 117682
2022-05-19 | May 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | East West Link -part of Auckland Accelerated Programme(AAP) | Property | Property - 331 | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | EWL has been subject to Supreme Court appeals and a decision is still pending. Once this has been received, the project will need to be rescoped and updated to confirm problem definition and the way forward. | -5 | -5 |  |  | 1.9 | 1.9 | 60027281 | 269877 | 60027281 | 117574
2022-05-25 | May 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Harewood Rd to Yaldhurst Rd 4 Laning | Property | Property | H_M | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project close. | 0 | 0 |  |  | 1.5 | 1.5 | 60465152 | 212337 | 60465152 | 117750
2022-05-30 | May 2022 Review | Cash flow adjustment | Debt Funding | Property purchase (local roads) | Auckland Transport | TNFG - North West HIF | Property | TNFG - NW HIF - Trig South (PROP) | HHH | H_H | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 programme monitor, this is a cost neutral cashflow adjustment to reflect the current forecast for this activity. | 0 | 0 |  |  | 5 | 1.4 | 332.264 | 263985 |  | 117726
2022-05-30 | May 2022 Review | Cash flow adjustment | Debt Funding | Property purchase (local roads) | Auckland Transport | TNFG - North West HIF | Property | TNFG - NW HIF - Redhills (PROP) | HHH | H_H | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 programme monitor, this is a cost neutral cashflow adjustment to reflect the current forecast for this activity. | 0 | 0 |  |  | 5 | 1.4 | 332.264 | 263983 |  | 117723
2022-05-27 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | Airport Access - Short-term Improvements | Implementation | Airport Access - Bus Priority Improvements - IMP | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 1.3 | 1.3 | 531.2606 | 260576 |  | 117663
2022-05-27 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | Auckland Metro Train Capacity | Implementation | Auckland Metro Train Capacity - Imp | H_M | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 2.8 | 2.8 | 531.2382 | 238206 |  | 117669
2022-05-27 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | Downtown Bus Improvements | Detailed Business Case | City Centre Bus Improvements | VH_M | HHH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  |  |  | 531.2698 | 269753 |  | 117670
2022-05-27 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | Low Emission Bus Programme | Implementation | Low Emission Bus Programme (Trial) - IMP | HHVL | HHVL | N | 9 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 0 | 0.1 | 531.2647 | 264665 |  | 117672
2022-05-27 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | SI - Metro - On Bus Connectivity | Implementation | SI - Metro - On Bus Connectivity | H_H | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 0 | 4.4 | 531.2718 | 271840 |  | 117675
2022-05-30 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Christchurch City Council | Cluster 6: Core PT Route/Facilities: SW Lincoln Road Phase 1 | Implementation |  | H_M | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Already approved funding for FY21/22 will not be used this financial year. Remainder has been transferred to following financial year. We are still looking at a cost scope increase however this adjustment is to ensure that the already approved funds are carried over. | 0 | 0 |  |  | 3.5 | 3.5 | 38572 | 233334 |  | 117624
2022-05-30 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | NZ Transport Agency | National Total Mobility Administration System | Construction | National TM Admin System | H_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cash flowing funds into 2022/23 as per instructions from Senior Advisor for Multimodal & Innovation team | 0 | 0 |  |  |  | 1.4 | 80002257, 80002108 | 225068 |  | 117602
2022-05-27 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Rapid Transit Infrastructure | Auckland Transport | Airport to Botany | Pre-implementation* | A2B Route Protection (Pre-Imp phase 1) | VHHL | VHML | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. This activity is unable to be claimed until the condition precedent is cleared. | 0 | 0 |  |  | 2.5 | 2.5 | 540.2604 | 260418 |  | 117664
2022-05-27 | May 2022 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | Glenvar / East Coast Road Improvements | Implementation | Glenvar / East Coast Rd Improvements - IMP | VHHM | VHHM | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 0 | 5.4 | 324.2383 | 238281 |  | 117662
2022-05-27 | May 2022 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | LRGF - Huapai / Kumeu SHA | Implementation | Kumeu/Huapai SHA - IMP | H_L | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | s noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. It is noted that a CSA has been signalled for this activity which will be undertaken when the pre-imp elements are completed. | 0 | 0 |  |  | 0 | 3.7 | 324.2384 | 238389 |  | 117653
2022-05-27 | May 2022 Review | Cash flow adjustment |  | Road improvements | Auckland Transport | Lincoln Road Corridor Improvement | Implementation | Lincoln Road Corridor Imp-Const | HHVH | HHVH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, the completion of this activity is indicated to slip, so this is a cost neutral cashflow change. This project is likely to increase in cost, but details are being worked through as part of the Design phase and a CSA will be progress closer to the time. | 0 | 0 |  |  | 7.5 | 7.5 | 324.219 | 218977 |  | 116508
2022-05-27 | May 2022 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | Lincoln Road Corridor Improvement | Pre-implementation* | Lincoln Road Corridor Imp-Design | HHVH | HHVH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 7.5 | 7.5 | 324.2191 | 219098 |  | 117651
2022-05-27 | May 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | Auckland Transport | Safe Speeds Programme | Implementation | Speed Mgmt - IMP - R2Z | VH_VH | VHHVH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. A CSA is being discussed for this activity which will be advanced and submitted in due course. | 0 | 0 |  |  | 0 | 12 | 324.2647 | 278712 |  | 117684
2022-05-27 | May 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | Auckland Transport | Safe Speeds Programme | Pre-implementation* | Speed Mgmt - Pre-Imp- R2Z | VH_VH | VHHVH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 0 | 12 | 324.2696 | 279201 |  | 117685
2022-05-30 | May 2022 Review | Cash flow adjustment | Debt Funding | Road improvements | Auckland Transport | TNFG - North West HIF | Implementation | TNFG - NW HIF - Trig South (IMP) | HHH | H_H | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 programme monitor, this is a cost neutral cashflow adjustment to reflect the current forecast for this activity. | 0 | 0 |  |  | 5 | 1.4 | 324.264 | 263984 |  | 117725
2022-05-27 | May 2022 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | Transport Network for Growth - Combined | Detailed Business Case | TNFG - Combined - DBC and Pre-lodgement | H_M | HHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 4.8 | 4.8 | 324.2682 | 268152 |  | 117660
2022-05-27 | May 2022 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | Wellesley Street Bus Improvements | Detailed Business Case | East-West Midtown PT Link - DBC | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 0 | 1.6 | 324.2434 | 243389 |  | 117661
2022-05-30 | May 2022 Review | Cash flow adjustment | Local road improvements | Road improvements | Hutt City Council | Hutt City Cross Valley Connection | Single-Stage Business Case |  | VHHL | VHHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The SSBC funding was only approved early 2022 by Waka Kotahi, work to be continued in FY22/23. | 0 | 0 |  |  | 0 | 5.3 |  | 276574 |  | 117622
2022-05-30 | May 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | East West Link -part of Auckland Accelerated Programme(AAP) | Pre-implementation* | Design | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | EWL has been subject to Supreme Court appeals and a decision is still pending. Once this has been received, the project will need to be rescoped and updated to confirm problem definition and the way forward. | 0 | 0 |  |  | 1.9 | 1.9 | 60026605 | 233292 | 60026605 | 117626
2022-05-30 | May 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | W2T Katikati Urban | Investigation |  | MML | MML | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving $620 from 2029 to 2022 to pay off one invoice. | -1 | -1 |  |  | 0 | 2.5 | 60202479 | 173249 | 60202479 | 117770
2022-05-24 | May 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (BOP) | W2T Waihi to Omokoroa (Safer Corridor) | Implementation |  | VHHL | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | adjusting forecats and bringing works forward as the programme is well ahead than planned. | 1 | 1 |  |  | 0 | 1 |  | 278524 | 60062260 | 117006
2022-05-16 | May 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Canterbury) | NZUP SH1 Tinwald Corridor Improvements | Pre-implementation* | NZ Upgrade Programme | VHHL | MMM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow some of the allocation to 22/23 FY | 0 | 0 |  |  | 4.6 | 4.6 | 60057074 | 238975 | 60057074 | 117569
2022-05-16 | May 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Canterbury) | SH1 Timaru to St Andrews | Pre-implementation* | SH1 Timaru to St Andrews | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow of $2,262,058 required to be moved to next FY due to feasibility taking longer than expected | 0 | 0 |  |  | 10 | 10 | 293 | 277337 | 60060985 | 117503
2022-05-19 | May 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Manawatu/Whanganui) | Accessing Central New Zealand SH3 Napier Road | Pre-implementation* | Pre-implementation RtZ | VHMVH | VHMVH | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $350,877 from 2022 to 2023, funds will not be spent this Fin Yr. | 0 | 0 |  |  | 10.2 | 10.2 |  | 281018 | 60067358 | 117573
2022-05-16 | May 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Otago) | SH1 Oamaru to Dunedin - (Hampden to Palmerston) | Pre-implementation* |  | MHL | HHM | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | PS a lot less than allocated. Transfer $1,258,022 into next year for quick wins | 0 | 0 |  |  | 0 | 1.6 |  | 278560 | 60062303 | 117568
2022-05-18 | May 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 South-East Hamilton Improvements | Construction | SH1 Cobham/Cambridge Improvements Construction | H_M | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | no tenders received so PW will start later than planned | -1 | -1 |  |  | 5.9 | 5.9 | 60033606 | 239051 | 60033606 | 117469
2022-05-19 | May 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH1 and Grey St IS | Pre-implementation* |  | VHHM | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Investigation work proposed for this year has been revised down | 0 | 0 |  |  | 10 | 10 | 22903 | 277334 | 60061021 | 117472
2022-05-16 | May 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH3 Awakino to Mt Messenger Corridor Improvements (Waikato) | Implementation | NZTA-R2Z | MML | HHL | N | 9 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow $762,729 from CY to Y1. Works cannot be completed by this construction season. | -3 | -3 |  |  | 1.5 | 1.5 |  | 278481 | 60062213 | 117324
2022-05-19 | May 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | Te Rapa Section | Construction | Te Rapa Pavement Repairs | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow $27,097,647 from CY to Y1, Resource constraints delays to surfacing repairs | 0 | 0 |  |  | 0 | 1.4 |  | 268112 | 60054171 | 117485
2022-05-19 | May 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (West Coast) | SH6 SH69 to Charleston | Pre-implementation* | SH6 SH69 to Charleston | HHL | VHHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow of $2,976,068 required to be moved to next FY due to feasibility taking longer than expected | -2 | -2 |  |  | 10 | 10 | 171 | 277368 | 60061100 | 117502
2022-05-16 | May 2022 Review | Cash flow adjustment | Local road maintenance | Structures component replacements | DOC (West Coast) | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | SPR |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Shifting wc 216 funding into wc 215. Original funding bid had mistakenly put funding for bridge components through wc216. Change does not affect overall funding allocation through West Coast programme. Disccussions with ACM Mark Weeds earlier this year and he accepted this reason for changing from 216 to 215. Cost neutral transaction, within MOR ALLOCATION. | 883949 | 450813 | [5 empty] | 275199 |  | 117442
2022-05-27 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Transitional Rail Infrastructure | Auckland Transport | AR - Fourth Main (Regional Rail) | Detailed Business Case | AR - Fourth Main - Papakura to Pukekohe DBC | M__ | M__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 1 | 1 | 545.2719 | 271942 |  | 117668
2022-05-27 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Transitional Rail Infrastructure | Auckland Transport | TR - Rail Network Growth Impact Management | Implementation | TR - Rail Network Growth Imp | H_L | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Mar22 Programme Monitor, this activity has slipped and so this is a NLTF neutral cashflow adjustment to reflect the latest forecast. | 0 | 0 |  |  | 5.4 | 5.4 | 545.2647 | 264698 |  | 117681
2022-05-30 | May 2022 Review | Cash flow adjustment | Public transport infrastructure | Transitional Rail Infrastructure | Waikato District Council | Huntly Station (Start Up Rail Service) | Construction | Huntly Below Track (plus platform) | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per advice from ACM | 0 | 0 |  |  | 0.5 | 0.5 |  | 266430 |  | 117585
2022-05-19 | May 2022 Review | Cash flow adjustment | Walking and cycling improvements | Walking facilities | Wellington City Council | Wellington Cycle Network - Eastern Package | Implementation | Kilbirnie - UCP Implementation - NLTF | VHHL | VHHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Delays due to lack of internal resources | 0 | 0 |  |  | 0 | 2.5 |  | 249023 |  | 117555
2022-05-11 | May 2022 Review | Cost Increase | Investment management (incl. Transport Planning) | Activity management planning improvement | Northland Regional Council | Activity Management Planning | Implementation | Regional Public Transport & Road Safety Planning | HHL | HHVH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Increasing funds in YR 3 to match CFO approval of $1,122,625 total for this AO. | 277304 | 149745 |  |  | 1 | 1 |  | 277132 |  | 117566
2022-05-30 | May 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Christchurch City Council | Major Cycleway: Nor'West Arc | Construction | Nor'West - 1c: Lincoln/Halswell to Annex Underpass | H_L | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project is nearing completion, freeing up Approval | -288902 | -147340 |  |  | 2 | 2 |  | 264498 |  | 117746
2022-05-30 | May 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Christchurch City Council | Major Cycleway: Nor'West Arc | Construction | Nor'West - 1b: Sparks Rd to Lincoln/Halswell | H_L | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project is nearing completion, Freeing up approval | -160032 | -81616 |  |  | 2 | 2 |  | 264497 |  | 117747
2022-05-30 | May 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Christchurch City Council | Major Cycleway: Nor'West Arc | Construction | Nor'West - 2: Annex Road/ Wigram Rd to University | H_L | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project is nearing completion, Freeing up approval | -899378 | -458682 |  |  | 2 | 2 |  | 244449 |  | 117743
2022-05-30 | May 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Christchurch City Council | Major Cycleway:South Express (Hornby Rail-Templeton to City) | Construction | South Express - Hagley Park to Upper Riccarton | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | project is nearing completion and there is a CSA on the other phase, this is freeing up approval on this phase | -137506 | -70128 |  |  | 1.5 | 1.5 | CPMS #26610 Sections 1 + 2 | 264492 |  | 117742
2022-05-30 | May 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Christchurch City Council | Northern Arterial Extension and Cranford Street Upgrade | Implementation | CNC Downstream Effects Cycleway links | H_L | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project is now complete, freeing up Approval | -622240 | -317342 |  |  | 2.3 | 2.3 |  | 269635 |  | 117745
2022-05-23 | May 2022 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Dunedin City Council | Wharf Street Safety Improvements | Implementation | Wharf St | H_L | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Additional funding required to complete project, transferred from LC/LR w/c allocation. Transfer is cost neutral for Waka Kotahi - $345,208 Waka Kotahi share. | 651336 | 345208 |  |  | 0 | 1.4 |  | 270081 |  | 117648
2022-05-16 | May 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Gisborne District Council | Emergency Event 10 September 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2021/22 as activity is claiming complete | -1882 | -1280 |  |  |  |  | Emergency Works 10 Sept 2018 (normal FAR | 267951 |  | 117567
2022-05-30 | May 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Gisborne District Council | Emergency Works: June 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Revised forecast reflects impact of COVID and recent state of emergencies - Cyclone Dovi and March 2022. FAR reduced from 88% to 67% | 0 | -672000 |  |  |  |  | Construction -Emergency Works: June 2020 Flood Damage | 278152 |  | 117751
2022-05-13 | May 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Porirua City Council | Emergency Works - December 2020 - Plimmerton and Pauatahanui | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Completed project | -341879 | -188033 | [5 empty] | 275607 |  | 117283
2022-05-16 | May 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Wellington City Council | Emergency Works July/August 2017 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Underspent related to covid delays/constrains | 0 | -340662 |  |  |  |  | EW (Normal FAR+20%) | 264675 |  | 117552
2022-05-23 | May 2022 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | Dunedin City Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | $656,800 reallocated to Wharf Street activity phase ID 270081 | -656800 | -345208 | [5 empty] | 276114 |  | 117647
2022-05-30 | May 2022 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Hauraki District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Delays to the start of the program (funding surety) Delays due to Covid-19 impacts on staff availability Implementation of Mahuta Rd North Bridge project delayed due to staff shortages and consent process (currently out on tender). Implementation of Pukekauri Rd Culverts project delayed as initial tender received zero bids. | 0 | -15260 | [5 empty] | 276160 |  | 117731
2022-05-30 | May 2022 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Hauraki District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Delays to the start of the program (funding surety) Delays due to Covid-19 impacts on staff availability Implementation of physical works projects subject to finalization of Speed Management Plan consultation. Consultation currently underway, but projects resulting from this will only be able to commence in the 2022/23 financial year. | 0 | -2419 | [5 empty] | 276157 |  | 117730
2022-05-24 | May 2022 Review | Cost Increase | State highway improvements | New roads | NZTA (Canterbury) | CHCH Southern Motorway HJR to Rolleston (Stage 2 & 3) | Construction | Implementation | H_M | H_L | N | 0 | Approved | Approved by Chief Financial Officer (CFO) |  | 23687957 | 23687957 |  |  | 2.4 | 1.5 | 60215381 | 200236 | 60215381 | 116608
2022-05-05 | May 2022 Review | Cost Increase | State highway improvements | New roads | NZTA (Wellington) | Wellington RoNS (7) - SH1 Peka Peka to Otaki Expressway | Construction |  | MHL | MHM | N | 7 | Approved | Approved by NZTA Board/Board Committee |  | 53135998 | 53135998 |  |  | 0.6 | 0.6 | 60217005 | 203544 | 60217005 | 116702
2022-05-12 | May 2022 Review | Cost Increase | Public transport services | Passenger services - ferry | Far North District Council | Government reduced public transport fares scheme (Crown) | Implementation | Hokianga ferry service - Reduced fares | HHL | VHHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Set FAR to 100% | 0 | 2502 | [5 empty] | 281226 |  | 117571
2022-05-30 | May 2022 Review | Cost Decrease | Public transport services | Passenger services - rail | Waikato Regional Council | Addendum to Te Huia SSBC-Interregional rail access post CRL | Single-Stage Business Case | Addendum to Te Huia SSC | HHL | VHHVH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2021/22 as activity is claiming complete | -293957 | -149918 |  |  | 0.5 | 0.5 | Addendum to Te Huia SSBC | 280356 |  | 117649
2022-05-13 | May 2022 Review | Cost Increase | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Land Transport Security Programme | Programme business case |  | VHH_ | VHHH | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Additional lot of funds approved by CFO in second POE. Please note that the earlier POE was for 2021/22 and this current POE is for 2022/23 as confirmed by Tony Brenand. The amounts are same. | 450000 | 450000 |  |  |  |  | 60065998 | 280016 |  | 117583
2022-05-17 | May 2022 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Safe Network Programme - Programme Case | Programme business case |  | H_L | V_L | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Fixing actual for 2000/21 to align SAP/TIO prior to project closure. | -196197 | -196197 |  |  |  |  | 60050535 | 266987 |  | 117606
2022-05-17 | May 2022 Review | Cost Increase | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Safe Network Programme - Programme Case | Programme business case |  | H_L | V_L | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving surplused funds from Safe Network Programme 2018-21 NLTP to clear the overspend | 725223 | 725223 |  |  |  |  | 60050535 | 266987 |  | 117327
2022-05-24 | May 2022 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | CHCH Southern Motorway HJR to Rolleston (Stage 2 & 3) | Property |  | H_M | H_L | N |  | Approved | Approved by Chief Financial Officer (CFO) |  | 5584159 | 5584159 |  |  | 2.4 | 1.5 | NB Includes pre-2013 costs which are missing in SAP | 200235 | 60455622 | 116609
2022-05-27 | May 2022 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Otago) | Kakaho Creek Realignment | Property |  | H_M | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Aligning TIO with SAP actuals | -571 | -571 |  |  | 2.7 | 2.7 | 60403682 | 246990 | 60403682 | 117771
2022-05-26 | May 2022 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Otago) | Kakaho Creek Realignment | Property |  | H_M | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | updating historic actuals for 13/14 & 14/15 to match SAP and adjusting 21/22 so that total is $50,811. This was requested by DG. | -329 | -329 |  |  | 2.7 | 2.7 | 60403682 | 246990 | 60403682 | 117769
2022-05-26 | May 2022 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Otago) | Kakaho Creek Realignment | Property |  | H_M | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reinstating funding to full amount of $50,811. Funding were surplused in earlier review. This reinstatement has been requested by Damien Grant | 31513 | 31513 |  |  | 2.7 | 2.7 | 60403682 | 246990 | 60403682 | 117768
2022-05-27 | May 2022 Review | Cost Decrease | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | Northern Busway Enhancements | Detailed Business Case | Northern Busway Ext - DBC | MHVL | VHML | N | 10 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This activity is complete so declaring surplus. | -183631 | -93652 |  |  | 0.3 | 0.3 | 531.2649 | 264938 |  | 117680
2022-05-11 | May 2022 Review | Cost Decrease | Public transport services | Public transport infrastructure and major renewals | Hamilton City Council | The Base Station (Start Up Rail Service) | Implementation | Frankton Station - Implementation | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Return of overclaimed funds. | -17295 | -8820 |  |  | 0.5 | 0.5 |  | 278212 |  | 117558
2022-05-13 | May 2022 Review | Cost Decrease | Public transport infrastructure | Public transport infrastructure and major renewals | NZTA (Auckland) | 20Connect (Southern and Eastern Airport Access Imps) | Implementation | 20Connect (SH20B Early Improvements) | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer: please move $88,842 from construction (60053046) to pre-imp (60042197) | -95953 | -95953 |  |  | 1.4 | 1 | (Early Works) | 264958 | 60053046 | 117204
2022-05-11 | May 2022 Review | Cost Decrease | Public transport services | Public transport operations and management | NZ Transport Agency | National Mode Shift Campaign | Single-Stage Business Case | SSBC National Mode Shift Campaign | MHVH | VHHM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Removing funds and creating another phase to fix incorrect work category (wc 524 to 421) | -97200 | -97200 |  |  | 5 |  |  | 281039 |  | 117562
2022-05-02 | May 2022 Review | Cost Increase | Public transport infrastructure | Rapid Transit Infrastructure | NZTA (Canterbury) | PT Futures MRT | Indicative Business Case |  | VHLL | HHL | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | Completion of IBC | 615245 | 615245 |  |  | 1 | 1 |  | 268114 | 60054249 | 117124
2022-05-30 | May 2022 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (West Coast) | SH7 Ahaura River Bridge Replacement | Implementation | Construction | H__ | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project substantially completed, and surplus allcoation of most of the risk items | -486476 | -486476 |  |  | 0 | 0 | 60030967 | 232575 | 60030967 | 117607
2022-05-11 | May 2022 Review | Cost Increase | External funding | Resilience improvements | NZTA (Taranaki) | RIO SH43 Manawawiri Stream Culvert IMPR | Implementation |  | H_L | H_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Approval from MOT to move funds within RIO SH43 Prgm.. Please move $53,941 from Project 142912020 - 60056089 Construction to 143002020 - 60056104 Construction. | 53941 | 53941 |  |  |  |  | Construction | 269737 | 60056104 | 117466
2022-05-11 | May 2022 Review | Cost Decrease | External funding | Resilience improvements | NZTA (Taranaki) | RIO SH43 Pohokura Stream Culvert IMPR | Implementation |  | H_L | M_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Approval from MOT to move funds within RIO SH43 Prgm.. Please move $1,110,559 from 143012020 - 60056108 Construction to 142922020 - 60056094 Construction, Funding Suplused. | -1110557 | -1110557 |  |  |  |  | Construction | 269738 | 60056108 | 117467
2022-05-11 | May 2022 Review | Cost Decrease | External funding | Resilience improvements | NZTA (Taranaki) | RIO SH43Preventative Maint Strategy R | Pre-implementation* |  | M_L | M_L | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Approval from MOT to move funds within RIO SH43 Prgm.. Please move $12,500 from Project 143032020 - 60056116 Pre-Implementation to 142922020 - 60056094 Construction. Funding Surplused. | -12500 | -12500 |  |  |  |  | Design | 269740 | 60056116 | 117468
2022-05-30 | May 2022 Review | Cost Decrease | Local road improvements | Road improvements | Christchurch City Council | Intersection Improvement:Cashmere/HoonHay/Worsley | Construction |  | M_H | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2021/22 as activity is claiming complete | -88908 | -45343 |  |  | 0 | 7.3 | 1346 | 237174 |  | 117765
2022-05-16 | May 2022 Review | Cost Decrease | External funding | Road improvements | Gisborne District Council | Tairawhiti Roading - LOS improvements (PGF2) East Cape Road | Construction | PGF2 Route 2 Gisborne Urban Zone | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | project finished release surplus funds | -830 | -830 |  |  | 1 | 1 | PGF2 Route 2 Gisborne Urban Zone | 269597 |  | 117551
2022-05-30 | May 2022 Review | Cost Decrease | Local road improvements | Road improvements | Hamilton City Council | 2015 Resolution Drive | Property | Resolution Drive Property | H_L* | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2021/22 as activity is claiming complete | -422335 | -215391 |  |  | 0 | 2.3 |  | 240070 |  | 117586
2022-05-10 | May 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (BOP) | NZUP Takitimu North Link Stage 1 | Implementation |  | H_L | HHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving $12.7M from Contingency phase to construction phase. Cost neutral change. | -13145535 | -13145535 |  |  | 2 | 2 |  | 278963 | 60063230 | 117444
2022-05-10 | May 2022 Review | Cost Increase | External funding | Road improvements | NZTA (BOP) | NZUP Takitimu North Link Stage 1 | Implementation | NZ Upgrade Programme | H_L | HHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Requesting $12.7m of contingency budget to construction phase. Cost neutral change. | 13145535 | 13145535 |  |  | 2 | 2 | 60057025 | 270272 | 60057025 | 117445
2022-05-16 | May 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Manawatu/Whanganui) | Otaki to North Levin - SH1/57 - southern section | Implementation |  | VHHL | HHVH | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 13910399 | 13910399 |  |  | 0 | 1.6 |  | 278530 | 60062283 | 117291
2022-05-12 | May 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Taranaki) | RIO SH43 Kahouri Stream Bridge Replacement | Implementation | Construction | M_L | M_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | MOT OK to move funds within RIO SH43 Prgm.. $562,809 from 142912020 - 60056089 Con to 142922020 - 60056094 Con, $1,110,559 from 143012020 - 60056108 Con to 142922020 - 60056094 Con, $12,500 from 143032020 - 60056116 Pre-Imp to 142922020 - 60056094 Con | 1685865 | 1685865 |  |  | 1 | 1 | 60056094 | 269735 | 60056094 | 117471
2022-05-11 | May 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Taranaki) | RIO SH43 Moki Tunnel IMPR | Implementation | Construction | M_L | M_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Approval from MOT to move funds within RIO SH43 Prgm. Please move $53,941 from 142912020 - 60056089 Construction to 143002020 - 60056104 Construction. Move additional $562,809 to 142922020 - 60056094 Construction. Funding suplused due to scope reduction | -616750 | -616750 |  |  | 1 | 1 | 60056089 | 269733 | 60056089 | 117470
2022-05-30 | May 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Taranaki) | SH43 Forgotten World Highway-Tangarakau Gorge Seal Extension | Implementation | PGF | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $98,344 from 60053425 - Construction to 60055673 - Pre-Implementation to cover wrongly coded Fees, so we can close out the Phase. | -98345 | -98345 |  |  | 0.7 | 0.7 |  | 255076 | 60053425 | 117632
2022-05-30 | May 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Taranaki) | SH43 Forgotten World Highway-Tangarakau Gorge Seal Extension | Pre-implementation* | PGF | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $98,344 from 60053425 - Construction to 60055673 - Pre-Implementation to cover wrongly coded Fees, so we can close out the Phase. | 98343 | 98343 |  |  | 0.7 | 0.7 |  | 269451 | 60055673 | 117633
2022-05-03 | May 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Waikato) | SH27 Mangawhero Bridge | Implementation |  | HML | HHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme advance from SH closure - allows forecast of surplus | -1095669 | -1095669 |  |  | 2.1 | 2.1 |  | 278478 | 60062210 | 117323
2022-05-13 | May 2022 Review | Cost Decrease | Local road improvements | Road improvements | Waimakariri District Council | Fernside Flaxton Roundabout | Pre-implementation* |  | VH_L | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project complete | -124961 | -94346 |  |  | 0 | 1.6 |  | 271680 |  | 117342
2022-05-27 | May 2022 Review | Cost Decrease | Public transport infrastructure | Transitional Rail Infrastructure | Auckland Transport | TR - Additional Power Feed | Single-Stage Business Case | TR - Akld Power Feed West - SSBC (AT) | H__ | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This activity is complete so declaring surplus. | -197955 | -197955 |  |  | 1 | 1 | 545.272 | 272004 |  | 117676
2022-05-27 | May 2022 Review | Cost Decrease | Public transport infrastructure | Transitional Rail Infrastructure | Auckland Transport | TR - Additional Power Feed | Single-Stage Business Case | TR - Akld Power Feed West - SSBC (KR) | H__ | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This activity is complete so declaring surplus. | -412314 | -412314 |  |  | 1 | 1 | 545.2647 | 264704 |  | 117677
2022-05-27 | May 2022 Review | Cost Decrease | Public transport infrastructure | Transitional Rail Infrastructure | Auckland Transport | TR - Auckland Integrated Rail Management Centre | Single-Stage Business Case | TR - Akld IRMC - SSBC (AT) | H_L* | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This activity is now complete so declaring surplus. | -91041 | -91041 |  |  | 1 | 1 | 545.2707 | 270702 |  | 117678
2022-05-27 | May 2022 Review | Cost Decrease | Public transport infrastructure | Transitional Rail Infrastructure | Auckland Transport | TR - Auckland Integrated Rail Management Centre | Single-Stage Business Case | TR - Akld IRMC - SSBC (KR) | H_L* | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This activity is complete so declaring surplus. | -4745 | -4745 |  |  | 1 | 1 | 545.2647 | 264706 |  | 117679
2022-05-27 | May 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | Auckland Transport | Safer Communities - Mangere Bridge | Implementation | SC - Mangere Bridge - IMP | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This activity is complete so declaring surplus. | -2193 | -1119 |  |  | 0 | 1.4 | 451.2647 | 264650 |  | 117686
2022-05-20 | May 2022 Review | Cost Increase | Walking and cycling improvements | Walking facilities | Auckland Transport | Safer Communities - Mt Roskill | Implementation | SC - Mt Roskill - IMP | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Further to email chain with Waka Kotahi, it has been agreed to reinstate the surplus previously declared to complete the activity due to the cost increases following project delays from COVID. | 1318714 | 672544 |  |  | 0 | 1.8 | 451.2608 | 260797 |  | 117642
2022-05-12 | May 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZ Transport Agency | Innovating Streets Programme 2021-24 | Implementation | Implementation - Funding allocated to AOs | HHL | VHHVH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Funds being allocated to CCC and WCC. | -277901 | -277901 |  |  | 1 | 1 |  | 279202 |  | 117565
2022-05-25 | May 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZ Transport Agency | Innovating Streets Programme 2021-24 | Implementation | Implementation - Funding allocated to AOs | HHL | VHHVH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Funds being moved to 1 council | -122542 | -122542 |  |  | 1 | 1 |  | 279202 |  | 117763
2022-05-11 | May 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZ Transport Agency | Innovating Streets Programme 2021-24 | Implementation | Implementation - Funding allocated to AOs | HHL | VHHVH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Funds being moved to the first 8 SfP council led projects. | -709649 | -709649 |  |  | 1 | 1 |  | 279202 |  | 117524
2022-05-17 | May 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZ Transport Agency | Innovating Streets Programme 2021-24 | Implementation | Implementation - Funding allocated to AOs | HHL | VHHVH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Funds being moved to 3 councils. | -355862 | -355862 |  |  | 1 | 1 |  | 279202 |  | 117605
2022-05-25 | May 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZ Transport Agency | Innovating Streets Programme 2021-24 | Implementation | Implementation - Funding allocated to AOs | HHL | VHHVH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Funds being moved to 1 councils | -116088 | -116088 |  |  | 1 | 1 |  | 279202 |  | 117762