## Instructions
Resouce efficiency opportunity register
This tool supports the opportunity identification and implementation process outlined in the Resource efficiency guideline for infrastructure delivery and maintenance. The purpose of this tool is to be a centralised opportunities register and a live initiatives tracker.
Identify & investigate – opportunity register
This tab should capture all opportunities identified during opportunity workshops/meetings. This acts as a register or database of all resource efficiency ideas generated by the project team for future reference. Where opportunities are taken forward for feasibility investigation, the outcome of those assessments can be recorded in this tab. Three initiatives have been pre-populated as an example. Further guidance on the expected information to be recorded is provided below:
ID – unique identification number.
Resource efficiency category – the broad resource efficiency category that the opportunity best fits in acknowledging that it may fit into more than one.
Opportunity description – a short description of the opportunity. More detail on the opportunity may be recorded elsewhere by the project team.
Priority – this should be based on the priority matrix used in the opportunities identification workshop/meeting. See the the Resource efficiency guideline for more details.
Senior owner – senior member of the project team responsible for the investigation of the opportunity. This person may assign tasks/ownership to others.
Date of investigation – date the investigation was carried out.
Investigation lead – person responsible for investigating the opportunity. This may or may not be the senior owner of the opportunity.
Feasibility outcome – the outcome of investigating the opportunity.
Feasibility summary points – main points of consideration for the opportunity as identified by the investigation phase.
Anticipated benefits – estimated benefits of the opportunity.
Success measures – potential measure(s) used to determine success of opportunity.
Implement – project initiatives tracker
Following agreement with the Waka Kotahi project manager, the initiatives to be taken forward for implementation are transferred to this tab. Note the wording changes from opportunities to initiatives in this tab as these are no longer something that could be implemented, but rather ideas that are going to be implemented. Three initiatives have been pre-populated as an example. Further guidance on the expected information to be recorded is provided below:
Implementation lead – may or may not be the investigation lead.
Status tracking – snap-shot of current status of initiative.
Actions to progress – shortlist of next known actions to progress the initiative.
Due dates of actions – due dates of actions listed in previous column.
Expected final completion date – expected completion date of the whole initiative.

## Identify & investigate
Opportunity register
Opportunity description |  |  |  |  | Investigation outcome
ID | Resource efficiency category (Materials, Energy, Waste, Water) | Opportunity description | Priority (A=High impact/low effort, B=Low impact/low effort, C=Low impact/high effort, D=High impact/high effort) | Senior owner | Date of investigation | Investigation lead | Feasibility outcome (Feasible to implement, Requires further investigation, Roadblocks to implementation) | Feasibility summary points | Anticipated benefits (if applicable) | Success measures (if applicable)
001 | Energy | Replace diesel generators with mains connection | A | John Smith | 2021-03-01 | John Smith | Feasible to implement | Low cost Technically feasible Good access to mains electricity | Reduce diesel use Reduce CO2 Cost savings | Number of diesel generators replaced
002 | Materials | Specify concrete with pozzolan cement replacement for all precast concrete panels | A | Sarah Smart | 2021-03-05 | Jane Brown | Requires further investigation | Potential for large CO2 savings Supplier cannot commit just yet | Reduce CO2 | Number of low carbon panels installed
003 | Waste | Appoint waste champion for each site | B | Sarah Smart | 2021-03-15 | Tom Williams | Feasible to implement | Dependent on volunteers Could also help with project culture | Reduce waste to landfill | Number of sites with waste champion
Note on D4: The opportunities evaluation grid is explained in section 3 of the Resource Efficiency Guideline.

## Implement
Project Initiatives Tracker
Initiative Description |  |  |  |  | Implementation Plan
ID | Resource efficiency category (Materials, Energy, Waste, Water) | Initiative description | Priority (A=High impact/low effort, B=Low impact/low effort, C=Low impact/high effort, D=High impact/high effort) | Senior owner | Implementation lead | Status tracking (On track, Behind schedule, Ahead, On hold, Completed) | Actions to progress | Due dates of actions | Expected final completion date
001 | Energy | Replace diesel generators with mains connection | A | John Smith | Frank Jones | On track | Schedule electrician Inform site foreman Cancel generator hire | 01/04/2021 01/04/2021 15/04/2021 | 2021-05-15
002 | Materials | Specify concrete with pozzolan cement replacement for all precast concrete panels | A | Sarah Smart | Jane Brown | On hold | Follow up call with supplier Send strength specs to structural engineer | 1/06/2021 01/04/2021 | TBC
003 | Waste | Appoint waste champion for each site | B | Sarah Smart | Tom Williams | Behind schedule | Survey project team for volunteers Provide training to volunteers | 15/04/2021 20/04/2021 | 2021-04-30
Note on D4: N/A: The opportunities evaluation grid is explained in section X of the Resource Efficiency Guideline.